## INSTRUCTIONS
INSTRUCTIONS:
| STEP 1 | DATA
| FALSE | Enter all DESIGN & DATA COLLECTION amounts invoiced that applies to customer. Use as reference the Proposals & Invoices.
If category does not applies to client, enter $0.
| FALSE | PERMITS & SERVICE FEES:
|  | FALSE | Permit Services: Enter Amount. Use as reference the Design Proposal.
|  | FALSE | Permit 1: Select EXC CATEGORICA ($75) or REA/DEA ($4,500)
|  | FALSE | Permit 3: Select $300
|  | FALSE | Liability Insurance: Select $2,000
|  | FALSE | Construction Inspection Fee: Enter Amount. Use as reference the Design Proposal.
| FALSE | PRODUCT OVERVIEW:
|  | FALSE | Qty of Product: Select Containers Qty that applies to the project.
|  | FALSE | Margin %: Select the margin discussed with Project Owner.
|  | FALSE | Product square ft: Enter product square footage. Use as reference the Design Plans.
| FALSE | DESCRIPTION: Enter the product model
| STEP 2 | PRODUCT LABOR & SUBCONTRACT
VALIDATE | FALSE | SUBCONTRACTORS: Enter all QUOTE amounts accordingly
VALIDATE | FALSE | LABOR: Enter & Review all planned hours
| STEP 3 | PRODUCT PHASE 1-5
VALIDATE | FALSE | Check all items that applies to the project. The unchecked items, please Enter 0 in quantities.
DOORS & FINISHES | FALSE | Items with Notes: Verify and enter the qty (according to plans) & ther cost of the items that applies to the project.
| STEP 4 | EXTERIOR & ADD-ONS
| FALSE | Enter the category, description, resource, and quote amount accordingly
| FALSE | Validate with project owner all the items that applies to the project.
ESTIMATE
| FALSE | Enter Client Name
| FALSE | Enter Version
| FALSE | Enter Model
| FALSE | Update Deliverables
| FALSE | Select Classification
| FALSE | Select Project Description
| FALSE | DESIGN & DATA COLLECTION: Select the dropdown that applies of each category
| FALSE | PERMITS & SERVICE FEES: Select the dropdown that applies of each category
| FALSE | EXTERIOR & ADD-ONS : Select the dropdown that applies of each category
PRINTING
| FALSE | Print: Workbook
| FALSE | Selection: Estimate and WBS
| FALSE | Paper Size: A3
| FALSE | Page Orientation: Portrait
| FALSE | Scale: Fit to width
| FALSE | Margins: Narrow

## DATA
DESIGN & DATA COLLECTION
Plans and Construction Documents | 26500
Soil Study | 5179
Survey and Topography | 2220
Bio-Garden Design | 0
Solar System Design | 0
PERMITS & SERVICE FEES
Municipal Patent | 13094.8831 |  | Permits
Permit Services (First 50%) | 2250 |  | 4500 | ENTER TOTAL
Permit Services (Last 50%) | 2250 |  |  | QUOTE AMOUNT
State Insurance Fund | 2661.15
Permit 1 (Ex. Categórica or REA/DEA) | 75
Permit 2 (Construction) | 2898.6332
Permit 3 (Use) | 300
Liability Insurance | 0
Construction Inspection Fee | 9000
PRODUCT OVERVIEW:
Qty of Product | 3
Margin % | 1.2
Contingency % | 1.15
Foundation | 55000
Steel Structure | 40000
Subcontracted | 126700
Labor | 47100
Materials | 51448.0512
Product Cost | 225248.0513 | 36649.6102
Product Price | 261897.6615
Product square ft | 0
Cost per square ft | 0
CLASSIFICATION
Paint by Numbers | 1.05 | [LOW RISK] KONTi and it's stakeholders are sure of what to do and how it is to be done. We feel confident on delivering the project early or under budget.
Quest | 1.1 | [MEDIUM RISK] KONTi and it's stakeholders are sure of what should be done, but unsure how we will achieve it. This project will need a strick control of time and cost. May have cost and time overruns.
Making a Movie | 1.15 | [MEDIUM RISK] KONTi and it's stakeholders are certain about how the project should proceed but not what needs to be done. Further definition may have cost and time overruns.
Lost in the Fog | 1.2 | [HIGH RISK] KONTi and it's stakeholders do not know what you want or how to achieve it. This type of project is new for us, therefore has not been attempted before. High probability of cost and time changes.
DESCRIPTION
Containers |  | The KONTi [ENTER MODEL] was designed for quick and simple container build and installation. Design specs, construction requirements, and build costs are standard. THIS IS A COST PLUS ESTIMATE AND IS SUBJECT TO CHANGE. |  | ENTER MODEL
Modulars |  | The KONTi [ENTER MODEL] model was designed for a modular steel beam and post construction to be assembled on site. Design specs, construction requirements, and build costs are standard. THIS IS A COST PLUS ESTIMATE AND IS SUBJECT TO CHANGE.
STAKEHOLDERS DATA
Stakeholders | Bill Rate | Description
Carla Gautier | 75 | Arquitect
Jorge Rosa | 50 | Project Manager
Michelle Telon | 25 | Lead Designer
Andrea Camacho | 50 | Construction Manager
North Steel | Subcontracted | Structural
JF Broker Unlimited Corp | Subcontracted | Container Purchase
MF Solution Corp | Subcontracted | Container Transport
Jose Super Exterminating | Subcontracted | Site and Container Fumigation
Solid Doors | Subcontracted | Exterior Windows & Doors
Geraldo Velez | Subcontracted | Electrical
AR Construction | Subcontracted | Kitchen
D&G Air Conditioning | Subcontracted | AC Installation
Jose Perez Aponte | Subcontracted | Foundation
Transcon Lightning System Inc. | Subcontracted | Solar Energy
Henry Mercedes | Subcontracted | Plumbing, Interiors, Foundation
Edgardo Javier | Subcontracted | Deck and Pergola
Soldadura Rizoma | Subcontracted | Welding

## PRODUCT LABOR & SUBCONTRACT
Note: Data Entry All items that are in red. If a red item does not apply, ignore.
SUBCONTRACTORS:
Phases | Category | Description | Resource | ENTER QUOTE
Phase 1 | Container Purchase | Purchase Container | JF Broker Unlimited Corp | 5000 |  | Interior
Phase 1 | Container Purchase | Transport Container to Shop | MF Solution Corp | 500 |  | 40000 | ENTER TOTAL
Phase 1 | Structural Prep | W&Ds framing cuts and installation | Soldadura Rizoma | 20000 |  |  | QUOTE AMOUNT
Phase 1 | Structural Prep | Container Reinforcement | North Steel | 7000
Phase 1 | Structural Prep | Red Oxide Primer on container | Edgardo Javier | 400
Phase 1 | Structural Prep | Container structural fumigation | Jose Super Exterminating | 500 |  | W&D
Phase 1 | Exterior Windows & Doors | Build | Solid Doors | 7500 |  | 15000 | ENTER TOTAL
Phase 2 | Exterior Windows & Doors | Installation | Solid Doors | 7500 |  |  | QUOTE AMOUNT
Phase 2 | Container Infrastructure | Plumbing | Henry Mercedes | 5200
Phase 2 | Container Infrastructure | Electrical | Geraldo Velez | 9800
Phase 2 | Container Infrastructure | Interior | Henry Mercedes | 20000 |  | Kitchen
Phase 2 | Kitchen | Build | AR Construction | 7500 |  | 15000 | ENTER TOTAL
Phase 3 | Kitchen | Installation | AR Construction | 7500 |  |  | QUOTE AMOUNT
Phase 3 | Interior Build | Plumbing Finishes | Henry Mercedes | 500
Phase 3 | Interior Build | AC units Installation | D&G Air Conditioning | 2200
Phase 3 | Interior Build | Interior | Henry Mercedes | 10000
Phase 3 | Bathroom | Bathroom Build | Henry Mercedes | 6000
Phase 4 | Container Finishes | Electrical finishes | Geraldo Velez | 1000
Phase 4 | Container Finishes | Interior | Henry Mercedes | 10000
Phase 4 | Container Finishes | Exterior Painting | Edgardo Javier | 400
Phase 4 | Container Installation | Transport Container to Site | MF Solution Corp | 15000
Phase 5 | Container Installation | Welding | Soldadura Rizoma | 3000
Phase 5 | Detailing | Door Installation |  | 3000
Phase 5 | Post Construction Cleanup | Last Clean Up |  | 2000
Enter Hrs & Review
LABOR:
Phases | Category | Description | Resource | Bill Rate | Planned Hrs | Total Cost
Phase 1 | Container Purchase | Project Management |  | 0 | 0 | 0
Phase 1 | Container Purchase | Coordination |  | 0 | 0 | 0
Phase 1 | Structural Prep | Project Management |  | 0 | 0 | 0
Phase 1 | Structural Prep | Coordination |  | 0 | 0 | 0
Phase 1 | Structural Prep | Punch List |  | 0 | 0 | 0
Phase 1 | Structural Prep | Structural Paint & Sealing |  | 0 | 0 | 0
Phase 1 | Structural Prep | Structural Paint & Sealing |  | 0 | 0 | 0
Phase 1 | Exterior Windows & Doors | Project Management |  | 0 | 0 | 0
Phase 1 | Exterior Windows & Doors | Coordination |  | 0 | 0 | 0
Phase 2 | Exterior Windows & Doors | Project Management |  | 0 | 0 | 0
Phase 2 | Exterior Windows & Doors | Coordination |  | 0 | 0 | 0
Phase 2 | Container Infrastructure | Project Management |  | 0 | 0 | 0
Phase 2 | Container Infrastructure | Coordination |  | 0 | 0 | 0
Phase 2 | Container Infrastructure | Punch List |  | 0 | 0 | 0
Phase 2 | Container Infrastructure | Wall Infrastructure |  | 0 | 0 | 0
Phase 2 | Container Infrastructure | Wall Infrastructure |  | 0 | 0 | 0
Phase 2 | Kitchen | Project Management |  | 0 | 0 | 0
Phase 2 | Kitchen | Coordination |  | 0 | 0 | 0
Phase 3 | Kitchen | Project Management |  | 0 | 0 | 0
Phase 3 | Kitchen | Coordination |  | 0 | 0 | 0
Phase 3 | Kitchen | Punch List |  | 0 | 0 | 0
Phase 3 | Bathroom | Project Management |  | 0 | 0 | 0
Phase 3 | Bathroom | Coordination |  | 0 | 0 | 0
Phase 3 | Bathroom | Punch List |  | 0 | 0 | 0
Phase 3 | Interior Build | Project Management |  | 0 | 0 | 0
Phase 3 | Interior Build | Coordination |  | 0 | 0 | 0
Phase 3 | Interior Build | Punch List |  | 0 | 0 | 0
Phase 3 | Interior Build | Wall Panels Installation |  | 0 | 0 | 0
Phase 3 | Interior Build | Wall Panels Installation |  | 0 | 0 | 0
Phase 3 | Interior Build | Mudding & Sanding |  | 0 | 0 | 0
Phase 3 | Interior Build | Mudding & Sanding |  | 0 | 0 | 0
Phase 3 | Interior Build | Flooring |  | 0 | 0 | 0
Phase 3 | Interior Build | Flooring |  | 0 | 0 | 0
Phase 3 | Interior Build | Priming |  | 0 | 0 | 0
Phase 3 | Interior Build | Priming |  | 0 | 0 | 0
Phase 4 | Container Finishes | Project Management |  | 0 | 0 | 0
Phase 4 | Container Finishes | Coordination |  | 0 | 0 | 0
Phase 4 | Container Finishes | Punch List |  | 0 | 0 | 0
Phase 4 | Container Finishes | Interior Painting & Final Details |  | 0 | 0 | 0
Phase 4 | Container Finishes | Interior Painting & Final Details |  | 0 | 0 | 0
Phase 4 | Container Finishes | Exterior Painting & Sealing |  | 0 | 0 | 0
Phase 4 | Container Finishes | Exterior Painting & Sealing |  | 0 | 0 | 0
Phase 4 | Container Installation | Project Management |  | 0 | 0 | 0
Phase 4 | Container Installation | Coordination |  | 0 | 0 | 0
Phase 4 | Container Installation | Punch List |  | 0 | 0 | 0
Phase 5 | Detailing | Project Management |  | 0 | 0 | 0
Phase 5 | Detailing | Coordination |  | 0 | 0 | 0
Phase 5 | Detailing | Punch List |  | 0 | 0 | 0
Phase 5 | Detailing | Transportation caused fixes |  | 0 | 0 | 0
Phase 5 | Detailing | Transportation caused fixes |  | 0 | 0 | 0
[6 empty] | 0 | TOTAL

## PRODUCT PHASES 1-5
Phases |  | Category | Description | Stakeholder | Class | Qty | Cost | Total Cost | Product Cost
Phase 1 | TRUE | Container Purchase | Purchase Container | JF Broker Unlimited Corp | Subcontracted | 1 | 5000 | 5000 | 15000
Phase 1 | TRUE | Container Purchase | Transport Container to Shop | MF Solution Corp | Subcontracted | 1 | 500 | 500 | 1500
Phase 1 | TRUE | Container Purchase | Coordination | Konti Design | Labor | 1 | 500 | 500 | 500
Phase 1 | TRUE | Structural Prep | Container Reinforcement | North Steel | Subcontracted | 1 | 7000 | 7000 | 7000
Phase 1 | TRUE | Structural Prep | W&Ds framing cuts and installation | North Steel | Subcontracted | 1 | 20000 | 20000 | 20000
Phase 1 | TRUE | Structural Prep | Acrylic Clear Primer & Sealer on frames, and Red Oxide Primer on container | Konti Design | Labor | 1 | 400 | 400 | 1200
Phase 1 | TRUE | Structural Prep | Purchase of AS-210 1 Gal. 100% Acrylic Clear Primer and Sealer | Konti Design | Materials | 1 | 17 | 18.955 | 56.865
Phase 1 | TRUE | Structural Prep | Purchase of 1 Gal. Oil Red Oxide Metal Primer | Konti Design | Materials | 2 | 100 | 223 | 669
Phase 1 | TRUE | Structural Prep | Miscellenous Materials | Konti Design | Materials | 1 | 500 | 557.5 | 1672.5
Phase 1 | TRUE | Structural Prep | Container structural fumigation | Jose Super Exterminating | Subcontracted | 1 | 500 | 500 | 1500
Phase 1 | TRUE | Structural Prep | Coordination | Konti Design | Labor | 1 | 500 | 500 | 500
Phase 1 | TRUE | Exterior Windows & Doors | First 50% deposit to start manufacturing | Solid Doors | Subcontracted | 1 | 7500 | 7500 | 7500
Phase 1 | TRUE | Exterior Windows & Doors | Coordination | Konti Design | Labor | 1 | 500 | 500 | 500
Phase 2 | TRUE | Exterior Windows & Doors | Installation | Solid Doors | Subcontracted | 1 | 7500 | 7500 | 7500
Phase 2 | TRUE | Exterior Windows & Doors | Coordination | Konti Design | Labor | 1 | 500 | 500 | 500
Phase 2 | TRUE | Container Infrastructure | Labor for Wall Infrastructure | Konti Design | Labor | 1 | 20000 | 20000 | 20000
Phase 2 | TRUE | Container Infrastructure | Studs 20GA 3 - 5/8 x 10 (Wall Divisions) | Konti Design | Materials | 25 | 10.75 | 299.6562 | 898.9688
Phase 2 | TRUE | Container Infrastructure | Studs 20GA 2 1/2 x 10 (Walls) | Konti Design | Materials | 80 | 7.2 | 642.24 | 1926.72
Phase 2 | TRUE | Container Infrastructure | Studs 20GA 2 1/2 x 8 (Ceiling) | Konti Design | Materials | 30 | 6.05 | 202.3725 | 607.1175
Phase 2 | TRUE | Container Infrastructure | Tracks 20GA 2 1/2 x 10 | Konti Design | Materials | 25 | 7.2 | 200.7 | 602.1
Phase 2 | TRUE | Container Infrastructure | Tracks 20GA 3 - 5/8 x 10 | Konti Design | Materials | 10 | 10.75 | 119.8625 | 359.5875
Phase 2 | TRUE | Container Infrastructure | Tracks & Studs Transportation | Konti Design | Materials | 1 | 100 | 111.5 | 334.5
Phase 2 | TRUE | Container Infrastructure | 3/4 in. x 4 ft. x 8 ft. Pine Pressure-Treated Plywood (Blockings) | Konti Design | Materials | 5 | 56.9 | 317.2175 | 951.6525
Phase 2 | TRUE | Container Infrastructure | 2 in x 4 in x 8 ft. Pine Pressure-Treated Wood (Interior Doors Post) | Konti Design | Materials | 10 | 7 | 78.05 | 234.15
Phase 2 | TRUE | Container Infrastructure | Insulation: Solar Guard RFSK/Foil 48"x125' (500sf) | Konti Design | Materials | 2 | 240 | 535.2 | 1605.6
Phase 2 | TRUE | Container Infrastructure | Miscellenous Materials | Konti Design | Materials | 1 | 600 | 669 | 2007
Phase 2 | TRUE | Container Infrastructure | Shower [TBD by client] | Konti Design | Materials | 1 | 300 | 334.5 | 1003.5
Phase 2 | TRUE | Container Infrastructure | Plumbing Infrastructure | Elvis Colon | Subcontracted | 1 | 5200 | 5200 | 5200
Phase 2 | TRUE | Container Infrastructure | Electrical Infrastructure | Geraldo Velez | Subcontracted | 1 | 9800 | 9800 | 9800
Phase 2 | TRUE | Kitchen | Coordination | Konti Design | Labor | 1 | 500 | 500 | 500
Phase 2 | TRUE | Kitchen | Starts Kitchen Build | AR Construction | Subcontracted | 1 | 7500 | 7500 | 7500
Phase 2 | TRUE | Kitchen | Sink [TBD by client] | Konti Design | Materials | 1 | 235 | 262.025 | 786.075
Phase 2 | TRUE | Kitchen | Stove [TBD by client] | Konti Design | Materials | 1 | 170 | 189.55 | 568.65
Phase 3 | TRUE | Interior Build | Labor for Interior Build | Konti Design | Labor | 1 | 10000 | 10000 | 10000
Phase 3 | TRUE | Interior Build | Plumbing Finishes in Kitchen & Bathroom | Elvis Colon | Subcontracted | 1 | 500 | 500 | 1500
Phase 3 | TRUE | Interior Build | AC units Installation | D&G Air Conditioning | Subcontracted | 1 | 2200 | 2200 | 2200
Phase 3 | TRUE | Interior Build | Drywall 4x10x5/8 (Walls) | Konti Design | Materials | 30 | 28 | 936.6 | 2809.8
Phase 3 | TRUE | Interior Build | Drywall 4x8x5/8 (Ceiling) | Konti Design | Materials | 12 | 23 | 307.74 | 923.22
Phase 3 | TRUE | Interior Build | Joint Compound Ultralight 4.5 GAL. | Konti Design | Materials | 5 | 25 | 139.375 | 418.125
Phase 3 | TRUE | Interior Build | Plycem 4 ft x 8 ft x 1/2 in | Konti Design | Materials | 5 | 42 | 234.15 | 702.45
Phase 3 | TRUE | Interior Build | 5 GAL White Acrylic Interior Drywall Plus Primer and Sealer | Konti Design | Materials | 2 | 88 | 196.24 | 588.72
Phase 3 | TRUE | Interior Build | Corner Bead Plast. 10' G/B | Konti Design | Materials | 50 | 4 | 223 | 669
Phase 3 | TRUE | Interior Build | Miscellenous Materials | Konti Design | Materials | 1 | 600 | 669 | 2007
Phase 3 | TRUE | Interior Build | Wall Panels Transport | Konti Design | Materials | 1 | 100 | 111.5 | 334.5
Phase 3 | TRUE | Interior Build | Baseboards: Panel PVC 1/4 Premium | Konti Design | Materials | 2 | 30 | 66.9 | 200.7
Phase 3 | TRUE | Interior Build | Luxury Vinyl Plank Flooring (20.06 sq ft / case) | Konti Design | Materials | 15 | 88 | 1471.8 | 4415.4
Phase 3 | TRUE | Interior Build | AC Units | Konti Design | Materials | 3 | 650 | 2174.25 | 2174.25
Phase 3 | TRUE | Bathroom | Bathroom Build | Waldemar Rosario | Subcontracted | 1 | 6000 | 6000 | 6000
Phase 3 | TRUE | Bathroom | 50 lb. Ultrafex 1 Tile Mortar with Polymer | Konti Design | Materials | 3 | 16 | 53.52 | 160.56
Phase 3 | TRUE | Bathroom | LASH Tile Leveling System Project Pack of 100 | Konti Design | Materials | 3 | 27 | 90.315 | 270.945
Phase 3 | TRUE | Bathroom | 10 lb Keracolor White unsanded grout | Konti Design | Materials | 3 | 9 | 30.105 | 90.315
Phase 3 | TRUE | Bathroom | Tiles (TBD - varied by client) | Konti Design | Materials | 1 | 1000 | 1115 | 3345
Phase 3 | TRUE | Bathroom | Saddle: White Double Hollywood 5 in. x 36 in. | Konti Design | Materials | 1 | 27 | 30.105 | 90.315
Phase 3 | TRUE | Bathroom | Stainless Steel Shower Floor Drain with Tile Insert | Konti Design | Materials | 1 | 80 | 89.2 | 267.6
Phase 3 | TRUE | Bathroom | 1 Gal. Quarry Tile Cleaner | Konti Design | Materials | 1 | 13 | 14.495 | 43.485
Phase 3 | FALSE | Bathroom | Vent (If applicable) | Konti Design | Materials | 0 | 0 | 0 | 0
Phase 3 | FALSE | Bathroom | Bathtub (If applicable) | Konti Design | Materials | 0 | 1000 | 0 | 0
Phase 3 | FALSE | Bathroom | Niches (If applicable) | Konti Design | Materials | 0 | 50 | 0 | 0
Phase 3 | TRUE | Bathroom | Coordination | Konti Design | Labor | 1 | 500 | 500 | 500
Phase 3 | TRUE | Kitchen | Coordination | Konti Design | Labor | 1 | 500 | 500 | 500
Phase 3 | TRUE | Kitchen | Installation of cabinets and top (Including sink and stove) | AR Construction | Subcontracted | 1 | 7500 | 7500 | 7500
Phase 4 | TRUE | Container Finishes | Electrical finishes Installation | Geraldo Velez | Subcontracted | 1 | 1000 | 1000 | 1000
Phase 4 | TRUE | Container Finishes | Labor for interior finishes | Konti Design | Labor | 1 | 10400 | 10400 | 10400
Phase 4 | TRUE | Container Finishes | Recessed Lights (5-Light Plug-In LED White Puck Light Kit) | Konti Design | Materials | 15 | 60 | 1003.5 | 1003.5
Phase 4 | TRUE | Container Finishes | Ceiling Fans (If applicable) | Konti Design | Materials | 4 | 250 | 1115 | 1115
Phase 4 | TRUE | Container Finishes | Pendant Lamps (If applicable) | Konti Design | Materials | 6 | 100 | 669 | 669
Phase 4 | TRUE | Container Finishes | Wall Plates (Switches) | Konti Design | Materials | 20 | 3 | 66.9 | 66.9
Phase 4 | TRUE | Container Finishes | Wall Plates (GFCI/USB Outlets) | Konti Design | Materials | 10 | 7 | 78.05 | 78.05
Phase 4 | TRUE | Container Finishes | Wall Plates (Regular Outlets) | Konti Design | Materials | 13 | 7 | 101.465 | 101.465
Phase 4 | FALSE | Container Finishes | 2" Aluminum Saddle for Entry (If applicable) | Konti Design | Materials | 0 | 0 | 0 | 0
Phase 4 | TRUE | Container Finishes | Miscellenous Materials | Konti Design | Materials | 1 | 600 | 669 | 2007
Phase 4 | TRUE | Container Finishes | 5 GAL i100 Toned-Base Interior Paint | Konti Design | Materials | 2 | 80 | 178.4 | 535.2
Phase 4 | TRUE | Container Finishes | Behr Ultra Exterior Paint Satin Deep | Konti Design | Materials | 2 | 252 | 561.96 | 1685.88
Phase 4 | TRUE | Container Finishes | Lanco Urethanizer | Konti Design | Materials | 3 | 151 | 505.095 | 1515.285
Phase 4 | TRUE | Container Finishes | General Cleaning | Konti Design | Materials | 1 | 100 | 111.5 | 334.5
Phase 2 | TRUE | Container Installation | Coordination | Konti Design | Labor | 1 | 500 | 500 | 500
Phase 2 | TRUE | Container Installation | Welding | Soldadura Rizoma | Subcontracted | 1 | 3000 | 3000 | 3000
Phase 2 | TRUE | Container Installation | Transport Container to Site | MF Solution Corp | Subcontracted | 1 | 15000 | 15000 | 15000
Phase 5 | TRUE | Detailing | Labor for transportation caused fixes | Konti Design | Labor | 1 | 500 | 500 | 1500
Phase 5 | TRUE | Detailing | Installation of vanity, toilet and fixtures | Elvis Colon | Subcontracted | 1 | 3000 | 3000 | 3000
Phase 5 | TRUE | Detailing | Purchase of vanity [TBD by client] | Konti Design | Materials | 2 | 400 | 892 | 892
Phase 5 | TRUE | Detailing | Purchase of toilet [TBD by client] | Konti Design | Materials | 2 | 300 | 669 | 669
Phase 5 | TRUE | Detailing | Purchase of bathroom faucet [TBD by client] | Konti Design | Materials | 2 | 150 | 334.5 | 334.5
Phase 5 | TRUE | Detailing | Purchase of kitchen faucet [TBD by client] | Konti Design | Materials | 1 | 220 | 245.3 | 735.9
Phase 5 | TRUE | Detailing | Purchase of other bathroom furniture (shower glass wall, other fixtures...) | Konti Design | Materials | 1 | 500 | 557.5 | 557.5
Phase 5 | TRUE | Detailing | Miscellenous Materials | Konti Design | Materials | 1 | 600 | 669 | 2007
Phase 5 | TRUE | Detailing | Doors + Frames + Gozne + Handles | Konti Design | Materials | 6 | 500 | 3345 | 3345
Phase 5 | TRUE | Detailing | Installation of doors | Konti Design | Subcontracted | 1 | 3000 | 3000 | 3000
Phase 5 | TRUE | Post Construction Cleanup | Last Clean Up | TBD | Subcontracted | 1 | 2000 | 2000 | 2000

## EXTERIOR & ADD-ONS
Note: Data Entry and classify items that applies to the Project, according to scope.
EXTERIOR & ADD-ONS
Category | Description | Stakeholder | ENTER QUOTE | BILL AMOUNT
Foundation | Considering High Phreatic Levels | Henry Mercedes | 55000 | 66000 | 40 | Job Days | 50 | gas
Site Electric | Pedestal and Connection |  | 10500 | 12600 | 8 | week | 10 | autoexpreso
Site Plumbing |  |  | 10000 | 12000 | 12 | weekly hrs | 20 | lunch
Bio Garden |  |  | 16650 | 19980 | 50 | rate | 80 | Consumables
Decking | Surface |  | 25000 | 30000 | 600 | CM Cost Weekly | 640 | Total Consumables
Site Work | Budget |  | 5000 | 6000 | 4800 | CM Cost Total | 5440 | CM & Consumables
Steel Structure | Deck Structure |  | 40000 | 48000
Decking | Wood Structure |  | 15000 | 18000 | 39000 | Jose Perez
|  |  | 0 | 0 | 5440 | CM/Consumable
|  |  | 0 | 0 | 0 | Bathroom/Storage Rental
|  |  | 0 | 0 | 5000 | Relleno
|  |  | 0 | 0 | 0 | Airbnb
|  |  | 0 | 0 | 1200 | Survey Stakeout
|  |  | 0 | 0 | 4360 | Contingency
|  |  | 0 | 0 | 50640 | Total
|  |  | 0 | 0 | 55000 | Total with Contingency
|  |  | 0 | 0
|  | 2400 | Transport to Site
|  | 2000 | Grua
|  | 4400 | Total
|  | 15000 | Presupuesto de Transporte
|  | 10600 | Remaining Budget for Lodging
|  | 7800 | Lodging
|  | 900 | Utilities
|  | 1900 | Difference

## PROJECT ESTIMATE
PROJECT SCOPE OVERVIEW
| CLIENT | Benito Colon |  | DELIVERABLES:
| DATE | 2026-01-21 | TRUE | Proposal
| VERSION | 1 | TRUE | Design & Construction Docs
| PRODUCT MODEL | L3 | FALSE | Product Delivery
CLASSIFICATION:
| Making a Movie | [MEDIUM RISK] KONTi and it's stakeholders are certain about how the project should proceed but not what needs to be done. Further definition may have cost and time overruns.
PROJECT DESCRIPTION:
The KONTi L1 model was designed for quick and simple container build and installation. Design specs, construction requirements, and build costs are standard. THIS IS A COST PLUS ESTIMATE AND IS SUBJECT TO CHANGE.
SUMMARY:
| ESTIMATED PROJECT COST |  |  | 522906.3277
| PAID TO DATE |  |  | 36149
| ESTIMATED PROJECT BALANCE |  |  | 486757.3277
ESTIMATED PROJECT COST BREAKDOWN:
| DESIGN AND DATA COLLECTION |  |  | 33899
| PERMITS & SERVICE FEES |  |  | 32529.6662
| PRODUCT (CONTAINERS) |  |  | 261897.6615
| EXTERIOR & ADD-ONS |  |  | 194580
| CONSTRUCTION CONTINGENCY |  |  | 68471.6492
Designated amount of money within a construction budget that is set aside to cover any unforseen costs, risks, events, or changes in scope that may affect the project's cost over the course of its life. This money is on reserve and is not allocated to any specific area of work. It is a form of risk management used to avoid cutting costs in other areas to keep the project's schedule and quality commitments. This contingency is intended to cover additional costs that might occur due to factors like design changes, unexpected site conditions, weather delays, or other unforeseen circumstances. Applies to Product (Containers) and Exterior & Add-ons.
NOTE: THIS A COST-PLUS ESTIMATE AND IS SUBJECT TO CHANGE.
PRE-CONSTRUCTION:
DESIGN & DATA COLLECTION |  |  |  | 33899
| Plans and Construction Documents |  | PAID | 26500
| Soil Study |  | PAID | 5179
| Survey and Topography |  | PAID | 2220
| Bio-Garden Design |  | N/A | 0
| Solar System Design |  | N/A | 0
PERMITS & SERVICE FEES |  |  |  | 32529.6662
| Municipal Patent (5%) |  | UPON APPROVAL | 13094.8831
| Permit Services (First 50%) |  | PAID | 2250
| Permit Services (Last 50%) |  | PENDING | 2250
| State Insurance Fund |  | UPON APPROVAL | 2661.15
| Permit 1 (Ex. Categórica) |  | PENDING | 75
| Permit 2 (Construction) |  | UPON APPROVAL | 2898.6332
| Permit 3 (Use) |  | UPON APPROVAL | 300
| Liability Insurance |  | UPON APPROVAL | 0
| Construction Inspection Fee |  | UPON APPROVAL | 9000
NOTE: THIS A COST-PLUS ESTIMATE AND IS SUBJECT TO CHANGE.
CONSTRUCTION:
PRODUCT (CONTAINERS) |  |  |  | 261897.6615
| Container Purchase |  | Phase 1 | 20400
| Structural Prep |  | Phase 1 | 30718.038
| Exterior Windows & Doors |  | Phase 1 & 2 | 19200 | 9600
| Container Infrastructure |  | Phase 2 | 54637.0755
| Interior Build |  | Phase 3 | 34731.798
| Bathroom |  | Phase 3 | 12921.864
| Kitchen |  | Phase 3 & 4 | 20825.67 | 10412.835
| Container Finishes |  | Phase 4 | 24614.136
| Container Installation |  | Phase 4 | 22200
| Detailing |  | Phase 5 | 19249.08
| Post Construction Cleanup |  | Phase 5 | 2400
EXTERIOR & ADD-ONS |  |  |  | 194580
| Foundation |  | Projected | 66000
| Appliances Purchase |  |  | 0
| Solar Energy |  |  | 0
| Site Electric |  | Projected | 12600
| Site Plumbing |  | Projected | 12000
| Bio Garden |  | Projected | 19980
| Pool |  |  | 0
| Steel Structure |  | Projected | 48000
| Decking |  | Projected | 30000
| Site Work |  | Projected | 6000
| Furniture & Interior Elements |  |  | 0
| Windows & Doors (Exterior Structure) |  |  | 0
| Closet Build |  |  | 0
NOTE: THIS A COST-PLUS ESTIMATE AND IS SUBJECT TO CHANGE.
TERMS AND CONDITIONS:
01) | This is a COST-PLUS estimate. Costs may vary month to month due to market flunctuation and this estimate cannot be consider as final.
02) | Before moving forward to the next phase, KONTI DESIGN will evaluate the cost of the following phase. In addition, KONTI DESIGN will send a Project Report and a COST-PLUS estimated projection for the following phase. The estimate will be always aligned with the initial COST-PLUS estimate sent before starting the construction phase.
03) | Estimate based on drawings and plans supplied on. Any deviation resulting from changes in drawings or site work, will be invoiced as an addition.
04) | Payments: Initial Deposit will be based on PHASE #1 of Initial COST-PLUS estimate. The following phases will be based on projected costs per phase that will be provided before moving forward to the next phase. Deposits shall be made before the innitiation of each phase.
05) | If payments are not received on time, KONTI DESIGN has the right to stop further execution, once cure appropiate equitable adjustments to contract sum or time shall be made.
06) | This conditions will take precedent over any conditions of any subcontract or purchase order, without exception.
07) | Invoices shall be paid in their total , without holding any reitanage %.
08) | We emphatically assert our right to relentlessly pursue legal recourse solely within the courts of San Juan, Puerto Rico. The client will be responsible for reimbursing all fees and expenses incurred during this procedure.
09) | Any questions, concerns, change orders, suggestion, etc should be directed to the Project Management Office in writing via email to carla@kontidesign.com, jorge@kontidesign.com and andrea@kontidesign.com.
10) | Site visits should be requested with at least two weeks of anticipation in order to secure the site and ensure civilian safety.
11) | Clients are ecouraged to stay clear from constrcution sites without proper escort.
ACCEPTED BY:
Benito Colon

## PROJECT ESTIMATE Wood Deck (hidden)
PROJECT SCOPE OVERVIEW
| CLIENT | Benito Colon |  | DELIVERABLES:
| DATE | 2026-01-21 | TRUE | Proposal
| VERSION | 2 | TRUE | Design & Construction Docs
| PRODUCT MODEL | L3 | FALSE | Product Delivery
CLASSIFICATION:
| Making a Movie | [MEDIUM RISK] KONTi and it's stakeholders are certain about how the project should proceed but not what needs to be done. Further definition may have cost and time overruns.
PROJECT DESCRIPTION:
The KONTi L1 model was designed for quick and simple container build and installation. Design specs, construction requirements, and build costs are standard. THIS IS A COST PLUS ESTIMATE AND IS SUBJECT TO CHANGE.
SUMMARY:
| ESTIMATED PROJECT COST |  |  | 492906.3277
| PAID TO DATE |  |  | 36149
| ESTIMATED PROJECT BALANCE |  |  | 456757.3277
ESTIMATED PROJECT COST BREAKDOWN:
| DESIGN AND DATA COLLECTION |  |  | 33899
| PERMITS & SERVICE FEES |  |  | 32529.6662
| PRODUCT (CONTAINERS) |  |  | 261897.6615
| EXTERIOR & ADD-ONS |  |  | 164580
| CONSTRUCTION CONTINGENCY |  |  | 63971.6492
Designated amount of money within a construction budget that is set aside to cover any unforseen costs, risks, events, or changes in scope that may affect the project's cost over the course of its life. This money is on reserve and is not allocated to any specific area of work. It is a form of risk management used to avoid cutting costs in other areas to keep the project's schedule and quality commitments. This contingency is intended to cover additional costs that might occur due to factors like design changes, unexpected site conditions, weather delays, or other unforeseen circumstances. Applies to Product (Containers) and Exterior & Add-ons.
NOTE: THIS A COST-PLUS ESTIMATE AND IS SUBJECT TO CHANGE.
PRE-CONSTRUCTION:
DESIGN & DATA COLLECTION |  |  |  | 33899
| Plans and Construction Documents |  | PAID | 26500
| Soil Study |  | PAID | 5179
| Survey and Topography |  | PAID | 2220
| Bio-Garden Design |  | N/A | 0
| Solar System Design |  | N/A | 0
PERMITS & SERVICE FEES |  |  |  | 32529.6662
| Municipal Patent (5%) |  | UPON APPROVAL | 13094.8831
| Permit Services (First 50%) |  | PAID | 2250
| Permit Services (Last 50%) |  | PENDING | 2250
| State Insurance Fund |  | UPON APPROVAL | 2661.15
| Permit 1 (Ex. Categórica) |  | PENDING | 75
| Permit 2 (Construction) |  | UPON APPROVAL | 2898.6332
| Permit 3 (Use) |  | UPON APPROVAL | 300
| Liability Insurance |  | UPON APPROVAL | 0
| Construction Inspection Fee |  | UPON APPROVAL | 9000
NOTE: THIS A COST-PLUS ESTIMATE AND IS SUBJECT TO CHANGE.
CONSTRUCTION:
PRODUCT (CONTAINERS) |  |  |  | 261897.6615
| Container Purchase |  | Phase 1 | 20400
| Structural Prep |  | Phase 1 | 30718.038
| Exterior Windows & Doors |  | Phase 1 | 19200
| Container Infrastructure |  | Phase 2 | 54637.0755
| Interior Build |  | Phase 3 | 34731.798
| Bathroom |  | Phase 3 | 12921.864
| Kitchen |  | Phase 4 | 20825.67
| Container Finishes |  | Phase 4 | 24614.136
| Container Installation |  | Phase 4 | 22200
| Detailing |  | Phase 5 | 19249.08
| Post Construction Cleanup |  | Phase 5 | 2400
EXTERIOR & ADD-ONS |  |  |  | 164580
| Foundation |  | Projected | 66000
| Appliances Purchase |  |  | 0
| Solar Energy |  |  | 0
| Site Electric |  | Projected | 12600
| Site Plumbing |  | Projected | 12000
| Bio Garden |  | Projected | 19980
| Pool |  |  | 0
| Steel Structure |  |  | 0
| Decking |  | Projected | 48000
| Site Work |  | Projected | 6000
| Furniture & Interior Elements |  |  | 0
| Windows & Doors (Exterior Structure) |  |  | 0
| Closet Build |  |  | 0
NOTE: THIS A COST-PLUS ESTIMATE AND IS SUBJECT TO CHANGE.
TERMS AND CONDITIONS:
01) | This is a COST-PLUS estimate. Costs may vary month to month due to market flunctuation and this estimate cannot be consider as final.
02) | Before moving forward to the next phase, KONTI DESIGN will evaluate the cost of the following phase. In addition, KONTI DESIGN will send a Project Report and a COST-PLUS estimated projection for the following phase. The estimate will be always aligned with the initial COST-PLUS estimate sent before starting the construction phase.
03) | Estimate based on drawings and plans supplied on. Any deviation resulting from changes in drawings or site work, will be invoiced as an addition.
04) | Payments: Initial Deposit will be based on PHASE #1 of Initial COST-PLUS estimate. The following phases will be based on projected costs per phase that will be provided before moving forward to the next phase. Deposits shall be made before the innitiation of each phase.
05) | If payments are not received on time, KONTI DESIGN has the right to stop further execution, once cure appropiate equitable adjustments to contract sum or time shall be made.
06) | This conditions will take precedent over any conditions of any subcontract or purchase order, without exception.
07) | Invoices shall be paid in their total , without holding any reitanage %.
08) | We emphatically assert our right to relentlessly pursue legal recourse solely within the courts of San Juan, Puerto Rico. The client will be responsible for reimbursing all fees and expenses incurred during this procedure.
09) | Any questions, concerns, change orders, suggestion, etc should be directed to the Project Management Office in writing via email to carla@kontidesign.com, jorge@kontidesign.com and andrea@kontidesign.com.
10) | Site visits should be requested with at least two weeks of anticipation in order to secure the site and ensure civilian safety.
11) | Clients are ecouraged to stay clear from constrcution sites without proper escort.
ACCEPTED BY:
Benito Colon

## CONTAINERS ESTIMATE (hidden)
PROJECT SCOPE OVERVIEW
| CLIENT | Frances Cartagena |  | DELIVERABLES:
| DATE | 2026-01-21 | TRUE | Proposal
| VERSION | 3 | TRUE | Design & Construction Docs
| PRODUCT MODEL | L3 | FALSE | Product Delivery
CLASSIFICATION:
| Quest | [MEDIUM RISK] KONTi and it's stakeholders are sure of what should be done, but unsure how we will achieve it. This project will need a strick control of time and cost. May have cost and time overruns.
PROJECT DESCRIPTION:
The KONTi L3 model was designed for quick and simple container build and installation. Design specs, construction requirements, and build costs are standard. THIS IS A COST PLUS ESTIMATE AND IS SUBJECT TO CHANGE.
| TOTAL ESTIMATED PROJECT COST |  |  | 328326.3277
| PAID TO DATE |  |  | 36224
| ESTIMATED PROJECT BALANCE |  |  | 292102.3277
| DESIGN AND DATA COLLECTION |  | 33899
| PERMITS & SERVICE FEES |  | 32529.6662
| PRODUCT (CONTAINERS) |  | 261897.6615
| EXTERIOR & ADD-ONS |  | 0
| CONSTRUCTION CONTINGENCY |  |  | 39284.6492
Designated amount of money within a construction budget that is set aside to cover any unforseen costs, risks, events, or changes in scope that may affect the project's cost over the course of its life. This money is on reserve and is not allocated to any specific area of work. It is a form of risk management used to avoid cutting costs in other areas to keep the project's schedule and quality commitments. This contingency is intended to cover additional costs that might occur due to factors like design changes, unexpected site conditions, weather delays, or other unforeseen circumstances.
NOTE: THIS A COST-PLUS ESTIMATE AND IS SUBJECT TO CHANGE.
PRE-CONSTRUCTION:
| DESIGN & DATA COLLECTION |  |  | 33899
| Plans and Construction Documents |  | PAID | 26500
| Soil Study |  | PAID | 5179
| Survey and Topography |  | PAID | 2220
| Bio-Garden Design |  | N/A | 0
| Solar System Design |  | PAID | 0
| PERMITS & SERVICE FEES |  |  | 32529.6662
| Municipal Patent (5%) |  | UPON APPROVAL | 13094.8831
| Permit Services (First 50%) |  | PAID | 2250
| Permit Services (Last 50%) |  | PENDING | 2250
| State Insurance Fund |  | UPON APPROVAL | 2661.15
| Permit 1 (Ex. Categórica) |  | PAID | 75
| Permit 2 (Construction) |  | UPON APPROVAL | 2898.6332
| Permit 3 (Use) |  | UPON APPROVAL | 300
| Liability Insurance |  | UPON APPROVAL | 0
| Construction Inspection Fee |  | UPON APPROVAL | 9000
NOTE: THIS A COST-PLUS ESTIMATE AND IS SUBJECT TO CHANGE.
CONSTRUCTION:
| PRODUCT (CONTAINERS) |  |  | 261897.6615
| Container Purchase |  | Phase 1 | 20400
| Structural Prep |  | Phase 1 | 30718.038
| Exterior Windows & Doors |  | Phase 1 | 19200
| Container Infrastructure |  | Phase 2 | 54637.0755
| Interior Build |  | Phase 3 | 34731.798
| Bathroom |  | Phase 3 | 12921.864
| Kitchen |  | Phase 4 | 20825.67
| Container Finishes |  | Phase 4 | 24614.136
| Container Installation |  | Phase 4 | 22200
| Detailing |  | Phase 5 | 19249.08
| Post Construction Cleanup |  | Phase 5 | 2400
| EXTERIOR & ADD-ONS |  |  | 0
| Foundation |  |  | 0
| Appliances Purchase |  |  | 0
| Solar Energy |  |  | 0
| Site Electric |  |  | 0
| Site Plumbing |  |  | 0
| Bio Garden |  |  | 0
| Pool |  |  | 0
| Steel Structure |  |  | 0
| Decking |  |  | 0
| Site Work |  |  | 0
| Furniture & Interior Elements |  |  | 0
| Windows & Doors (Exterior Structure) |  |  | 0
| Closet Build |  |  | 0
NOTE: THIS A COST-PLUS ESTIMATE AND IS SUBJECT TO CHANGE.
TERMS AND CONDITIONS:
01) | This is a COST-PLUS estimate. Costs may vary month to month due to market flunctuation and this estimate cannot be consider as final.
02) | Before moving forward to the next phase, KONTI DESIGN will evaluate the cost of the following phase. In addition, KONTI DESIGN will send a Project Report and a COST-PLUS estimated projection for the following phase. The estimate will be always aligned with the initial COST-PLUS estimate sent before starting the construction phase.
03) | Estimate based on drawings and plans supplied on. Any deviation resulting from changes in drawings or site work, will be invoiced as an addition.
04) | Payments: Initial Deposit will be based on PHASE #1 of Initial COST-PLUS estimate. The following phases will be based on projected costs per phase that will be provided before moving forward to the next phase. Deposits shall be made before the innitiation of each phase.
05) | If payments are not received on time, KONTI DESIGN has the right to stop further execution, once cure appropiate equitable adjustments to contract sum or time shall be made.
06) | This conditions will take precedent over any conditions of any subcontract or purchase order, without exception.
07) | Invoices shall be paid in their total , without holding any reitanage %.
08) | We emphatically assert our right to relentlessly pursue legal recourse solely within the courts of San Juan, Puerto Rico. The client will be responsible for reimbursing all fees and expenses incurred during this procedure.
09) | Any questions, concerns, change orders, suggestion, etc should be directed to the Project Management Office in writing via email to carla@kontidesign.com, jorge@kontidesign.com and andrea@kontidesign.com.
10) | Site visits should be requested with at least two weeks of anticipation in order to secure the site and ensure civilian safety.
11) | Clients are ecouraged to stay clear from constrcution sites without proper escort.
ACCEPTED BY:
Frances Cartagena

## WBS
WORK BREAKDOWN STRUCTURE (WBS)
Phase: Containers Build
Project Owner |  | Project Manager |  | Construction Manager
Carla Gautier |  | Jorge Rosa |  | Andrea Camacho
60718.038 |  | 64237.0755 |  | 58066.497 |  | 57226.971 |  | 21649.08
PHASE #1 |  | PHASE #2 |  | PHASE #3 |  | PHASE #4 |  | PHASE #5
1.1 Container Purchase |  | 2.1 Infrastructure |  | 3.1 Interior Build |  | 4.1 Kitchen |  | 5.1 Detailing
- | Purchase of Container | - | Metal framing | - | Panels | - | Installation | - | Bathroom Furniture & Fixtures
- | Transport to shop | - | Insulation | - | Mudding & Sanding | - | Stove & Sink Installation | - | Toilet Purchase & Installation
1.2 Structural Prep |  | - | Blockings | - | Flooring | 4.2 Finishes |  | - | Vanity Purchase & Installation
- | Frame & Cuts | - | Plumbing Infrastructure | - | AC Units (If applicable) | - | Ceiling Fan (If applicable) | - | Faucets Purchase & Installation
- | Frames Sealing | - | Electrical Infrastructure | - | Primer | - | Recessed Lights (If applicable) | - | Other Purchase & Installation
- | Red Oxide Primer | - | Gypsum Board Panels | 3.2 Bathroom |  | - | Pendant Lamps | - | Interior Doors
- | Fumigation | 2.2 Container Installation |  | - | Tiles | - | Interior Painting | - | Transportation fixes
1.3 Exterior Windows & Doors |  | - | Transport to Site | 3.3 Kitchen |  | - | Roof sealing and heat... | 5.2 Post Construction Clean-up
- | Manufacturing |  |  | - | Manufacturing | - | Exterior Painting
- | Installation

## PRESENTATION
ESTIMATE |  | ACTUAL
261897.6615 |  | 261897.6615
| PHASE ONE | 60718.038 | PAID Invoice #1
| Container Purchase | 20400
| Structural Prep | 30718.038
| Exterior Windows & Doors | 9600
| PHASE TWO | 64237.0755 | PAID Invoice #2
| Exterior Windows & Doors | 9600
| Container Infrastructure | 54637.0755
| PHASE THREE | 58066.497 | PAID Invoice #2
| Interior Build | 34731.798
| Bathroom | 12921.864
| Kitchen | 10412.835
| PHASE FOUR | 57226.971
| Container Finishes | 24614.136
| Kitchen | 10412.835
| Container Installation | 22200
| PHASE FIVE | 21649.08
| Detailing | 19249.08
| Post Construction Cleanup | 2400

## BUDGET
Budget |  | 0
Product Build | 261897.6615
Ext & Add-on:
Foundation
Appliances Purchase
Solar Energy
Site Electric
Site Plumbing
Bio Garden
Pool
Steel Structure
Decking
Site Work
Furniture & Interior Elements
Windows & Doors (Exterior Structure)
Closet Build
PM Site Visits
Difference |  | -261897.6615

## ESTIMATE OLD (hidden)
PROJECT SCOPE OVERVIEW
| CLIENT | Enter Client Name |  | DELIVERABLES:
| DATE | 2026-01-21 | FALSE | Proposal
| VERSION | Enter Version | FALSE | Design & Construction Docs
| PRODUCT TYPE | Enter Type | FALSE | Product Delivery
CLASSIFICATION:
| Paint by Numbers | [LOW RISK] KONTi and it's stakeholders are sure of what to do and how it is to be done. We feel confident on delivering the project early or under budget.
PROJECT DESCRIPTION:
The KONTi [ENTER MODEL] model was designed for a modular steel beam and post construction to be assembled on site. Design specs, construction requirements, and build costs are standard. THIS IS A COST PLUS ESTIMATE AND IS SUBJECT TO CHANGE.
| TOTAL PROJECT COST |  |  | 14036.15
| DESIGN AND DATA COLLECTION |  | 0
| PERMITS & SERVICE FEES |  | 14036.15
| CONTAINER(S) |  | 0
| EXTERIOR & ADD-ONS |  | 0
| CONSTRUCTION CONTINGENCY |  |  | 16141.5725
Designated amount of money within a construction budget that is set aside to cover any unforseen costs, risks, events, or changes in scope that may affect the project's cost over the course of its life. This money is on reserve and is not allocated to any specific area of work. It is a form of risk management used to avoid cutting costs in other areas to keep the project's schedule and quality commitments. This contingency is intended to cover additional costs that might occur due to factors like design changes, unexpected site conditions, weather delays, or other unforeseen circumstances.
NOTE: THIS A COST-PLUS ESTIMATE AND IS SUBJECT TO CHANGE.
DESIGN AND PERMITS:
| DESIGN AND DATA COLLECTION |  |  | 0
| Plans and Construction Documents |  | 0
| Soil Study |  | 0
| Survey and Topography |  | 0
| Solar Energy Design |  | 0
| PERMITS & SERVICE FEES |  |  | 14036.15
| Municipal Patent (5%) |  | 0
| Permit Services |  | 0
| Permit 1 (Ex. Categórica) |  | 75 | recuerda hacer el drop down aqui.. con REA/DEA
| Permit 2 (Construction) |  | 0
| Permit 3 (Use) |  | 300
| Mandatory State Insurance |  | 2661.15
| Liability Insurance |  | 2000
| Construction Inspection Fee |  | 9000
Note: The projected costs have been calculated in line with the construction percentages stipulated by the Puerto Rico government and remain the exclusive obligation of the owner. KONTi Design assumes no liability for ultimate expenses ascertained by pertinent authorities and local bodies, contingent on the furnished documentation. Should the KONTi Design team need to secure financing for these outlays on behalf of the client, a coordination fee of 20% will be implemented, with the exception of the Municipal Patent, which will encompass a 10% coordination fee.
CONSTRUCTION:
| CONTAINER(S): PHASE 1 |  |  | 0
Container Purchase
Structural Prep
Exterior Windows & Doors (Purchase)
| Coordination Fee |  | 0
Includes: Purchase & Transport to shop; Cuts & Framing, Red Oxide , Extermination; Start of manufacturing of exterior windows & doors
| CONTAINER(S): PHASE 2 |  |  | 0
Container Infrastructure
Exterior Windows & Doors (Installation)
Kitchen Build
| Coordination Fee |  | 0
Includes: Exterior Windows & Doors installation; Metal framing, insulation, plumbing & electrical infrastructure; Start Kitchen Manufacturing
| CONTAINER(S): PHASE 3 |  |  | 0
Bathrooms
Container Build
Kitchen Installation
| Coordination Fee |  | 0
Includes: Gypsum Installation, Mudding & Sanding, Flooring, Priming paint; AC units installation; Tiles, Shower Head & Drain Installation; Kitchen cabinets, tops, sink & stove installation
| CONTAINER(S): PHASE 4 |  |  | 0
Transportation
Container Finishes
| Coordination Fee |  | 0
Includes: Electrical finishes; Interior & Exterior Painting; Roof sealing & heat treatment; Interior doors purchase & installation; transport to site
| CONTAINER(S): PHASE 5 |  |  | 0
| Detailing |  | 0
| Post Construction Cleanup |  | 0
| Coordination Fee |  | 0
Includes: Purchase & Installation of vanity, toilet, faucets; Site Punchlist final details; Last Clean up; Product hand-off
| EXTERIOR AND ADD-ONS |  |  | 0
| Foundation |  | 0
| Appliances Purchase |  | 0
| Solar Energy |  | 0
| Site Electric |  | 0
| Site Plumbing |  | 0
| Bio-Garden |  | 0
| Pool |  | 0
| Steel Structure |  | 0
| Decking |  | 0
| Site Work |  | 0
| Furniture and Interior Design Elements |  | 0
| Coordination Fee |  | 0
Note: Each item in the "Exterior" and "Add-Ons" categories has been quoted separately. The client is free to source quotes and manage the coordination of the work independently. In cases where Konti Design is not responsible for project coordination, we will not assume responsibility for the job.
CONDITIONS AND CLARIFICATIONS:
1) | This is a COST-PLUS estimate. Costs may vary month to month due to market flunctuation and this estimate cannot be consider as final.
2) | Before moving forward to the next phase, KONTI DESIGN will evaluate the cost of the following phase. In addition, KONTI DESIGN will send a Project Report and a COST-PLUS estimated projection for the following phase. The estimate will be always aligned with the initial COST-PLUS estimate sent before starting the construction phase.
3) | Estimate based on drawings and plans supplied on. Any deviation resulting from changes in drawings or site work, will be invoiced as an addition.
4) | Payments: Initial Deposit will be based on PHASE #1 of Initial COST-PLUS estimate. The following phases will be based on projected costs per phase that will be provided before moving forward to the next phase. Deposits shall be made before the innitiation of each phase.
5) | If payments are not received on time, KONTI DESIGN has the right to stop further execution, once cure appropiate equitable adjustments to contract sum or time shall be made.
6) | This conditions will take precedent over any conditions of any subcontract or purchase order, without exception.
7) | Invoices shall be paid in their total , without holding any reitanage %.
8) | We emphatically assert our right to relentlessly pursue legal recourse solely within the courts of San Juan, Puerto Rico. The client will be responsible for reimbursing all fees and expenses incurred during this procedure.
ACCEPTED BY: