## Henry Mercedes
CONTRACTOR MONITORING REPORT:
H&G Construction
ENTER START DATE | TODAY'S DATE | APPROVED DELAY DAYS | NEW DAYS
2026-01-12 | 2026-01-21 | 0 | 84
ENTER DAYS | INITIAL FINISH DATE | NEW FINISH DATE | ACTUAL DAYS
84 | 2026-04-06 | 2026-04-06 | 9
Category | Date | Week | Status | Phases | Task | Link (Photos)
WEEKLY PLANNING | 2026-01-12 | Week 1: Interior Infrastructure | Not Started | Phase 1 | Aislation & Flooring Tracks; KONTi needs to verify room dimensions | 2026-01-12
| 2026-01-19 | Week 2:
NOTABLE DELAYS |  |  |  | 0
0
0
0
0
0
0
0
CHANGE ORDERS |  |  |  | 0
0
0
0
0
0
0
0
0
0
RELEVANT CLIMATE CONDITIONS |  |  |  | 0
0
0
0
0
0
0
0
0
0
BREACH OF CONTRACT |  |  |  | 0
0
0
0
0
0
0
0
0
CORRECTIVE ACTIONS |  |  |  | 0
0
0
0
0
0
0
0
0
0
Formulas:
APPROVED DELAY DAYS = [TODAY'S DATE]+D5

## Soldadura Rizoma
CONTRACTOR MONITORING REPORT:
JORDY MEDINA
ENTER START DATE | TODAY'S DATE | APPROVED DELAY DAYS | NEW DAYS
2025-04-08 | 2026-01-21 | 31 | 121
ENTER DAYS | INITIAL FINISH DATE | NEW FINISH DATE | ACTUAL DAYS
90 | 2025-07-07 | 2025-08-07 | 288
Category | Date | Description | Status | Days (#) | Notes | Link (Evidence)
NOTABLE DELAYS | 6/29/25 - 7/2/25 | Enfermo con Mycoplasma | Approved | 4 | Como quiera trabajó enfermo y con lluvias los días siguitentes | I. Notable Delays
| 7/10/25 - 7/11/25 | Movido a soldar bases de calentador solar en Rio Grande | Approved | 2
CHANGE ORDERS
RELEVANT CLIMATE CONDITIONS | 6/7/25 - 6/9/25 | Atraso por lluvias | Approved | 3 |  | III. Climate Conditions
| 6/22/25 - 6/24/25 | Atraso por lluvias | Approved | 3
| 7/2/25 - 7/4/25 | Atraso por lluvias | Approved | 3
| 7/7/25 - 7/8/25 | Atraso por lluvias | Approved | 2
| 7/14/25 - 7/15/25 | Atraso por lluvias | Approved | 2
| 2025-07-22 | Atraso por lluvias | Approved | 1
| 2025-08-04 | Atraso por lluvias | Approved | 1
| 8/6/25 - 8/7/25 | Atraso por lluvias | Approved | 2
| 2025-08-09 | Atraso por lluvias | Approved | 1
| 8/16/25 - 8/18/25 | Atraso por lluvias de huracán Erin | Approved | 2
BREACH OF CONTRACT
CORRECTIVE ACTIONS | 2025-06-17 | Trabajar de noche para aprovechar menos lluvia | Approved | 1 |  | V. Corrective Actions
| 2025-06-23 | Ajustar alineación de vagones | Approved | 1
| 8/6/25 - 8/8/25 | comprar más material y prepararlo para bordes de vagón interior y exterior, gosnes y otras zonas que no se anticiparon y él notó y quiere solucionarlo | Approved | 3
Formulas:
TODAY'S DATE = B5+[ENTER START DATE]
APPROVED DELAY DAYS = [TODAY'S DATE]+D5

## Ing Jose Aponte
CONTRACTOR MONITORING REPORT:
ING. JOSE APONTE
ENTER START DATE | TODAY'S DATE | APPROVED DELAY DAYS | NEW DAYS
2025-06-27 | 2026-01-21 | 8 | 29
ENTER DAYS | INITIAL FINISH DATE | NEW FINISH DATE | ACTUAL DAYS
21 | 2025-07-18 | 2025-07-26 | 208
Category | Date | Description | Status | Days (#) | Notes | Link (Evidence)
NOTABLE DELAYS | 6/30/25 - 7/8/25 | buscando información de medidas de pedestal | Approved | 7
| 2025-07-07 | mordida de perro vecino | Approved | 1
0
0
0
0
0
0
CHANGE ORDERS |  |  |  | 0
0
0
0
0
0
0
0
0
0
RELEVANT CLIMATE CONDITIONS |  |  |  | 0
0
0
0
0
0
0
0
0
0
BREACH OF CONTRACT | 2025-07-11 | Se hizo cimiento de pedestal y envarillado pero no se comenzó pedestal, ni sabemos sobre codo ni detalles del alambrado dentro de la tubería eléctrica del pedestal | Not Started | 2
| 7/22/25 - 8/12/25 | Abandono de trabajo | Denied | 14
0
0
0
0
0
0
0
0
CORRECTIVE ACTIONS |  |  |  | 0
0
0
0
0
0
0
0
0
0
Formulas:
TODAY'S DATE = B5+[ENTER START DATE]
APPROVED DELAY DAYS = [TODAY'S DATE]+D5

## Ing. Aponte (hidden)
CONTRACTOR MONITORING REPORT:
Construction Project Delays
Contractor Name: Ing. Aponte
Category | Date | Description | Status | Notes | Link (Evidence)
NOTABLE DELAYS |  |  | Denied
CHANGE ORDERS
RELEVANT CLIMATE CONDITIONS
BREACH OF CONTRACT
CORRECTIVE ACTIONS