## ProgressReport
PROGRESS REPORT: |  | BENITO COLON
ACTIVITIES TO COMPLETE |  | ACTIVITIES DONE |  | % OF COMPLETION |  | STATUS
39 |  | 7 |  | 17.95% |  | #NAME?
| DESIGNER: | CARLA GAUTIER | CONSTRUCTION MANAGER: | NAINOSHKA PAGAN | PROJECT MANAGER: | JORGE ROSA
|  |  |  | START DATE: | END DATE:
PHASE 1:
PHASE 2A:
PHASE 2B:
PHASE 3A:
PHASE 3B:
PHASE 4:

## Punchlist
PUNCHLIST BY PHASE:
Construction Estimate Link
Phases |  | Category | Description | Status | Stakeholder | Notes | Link
PHASE 1 | TRUE | Container Purchase | Purchase Container | DONE | JF Broker Unlimited Corp | Use link to see reference photos of this Category. | Container Photos
| TRUE | Container Purchase | Transport Container to Shop | DONE | MF Solution Corp
| TRUE | Structural Prep | Windows & Doors framing cuts | DONE | Soldadura Rizoma | Use link to see reference photos of this Category. | Structural Prep Photos
| TRUE | Structural Prep | Frames Installation | DONE | Soldadura Rizoma
| FALSE | Structural Prep | Acrylic Clear Primer and Sealer on frames |  | Soldadura Rizoma
| FALSE | Structural Prep | Red Oxide Primer on container |  | Soldadura Rizoma
| TRUE | Structural Prep | Container structural fumigation | DONE | JP Exterminating | Use link to see Fumigation Warranty | Fumigation Warranty
| TRUE | Exterior Windows & Doors | Starts manufacturing of windows & doors | DONE | All Screens Doors & Windows | W&D details in Purchase Agreement signed by Client. | Windows & Doors Purchase Agreement Signed
PHASE 2 | FALSE | Exterior Windows & Doors | Installation |  | All Screens Doors & Windows | Use link to see reference photos of this Category. | Windows & Doors Photos
| FALSE | Interior Infrastructure | Metal framing for walls and ceiling |  | H&G Construction | Use link to see reference photos of this Category. | Interior Infrastructure Photos
| FALSE | Interior Infrastructure | Insulation Installation |  | H&G Construction
| FALSE | Interior Infrastructure | Blocking for cabinets, shelving, ACs... |  | H&G Construction
| FALSE | Interior Infrastructure | Gypsum Board |  | H&G Construction
| FALSE | Interior Infrastructure | Wood Posts for Interior Doors |  | H&G Construction
| FALSE | Plumbing Infrastructure | Interior Plumbing installation |  | H&G Construction | Use link to see reference photos of this Category. | Plumbing Photos
| FALSE | Electrical Infrastructure | Switches, Receptacles, Breaker Box... |  | H&G Construction | Use link to see reference photos of this Category. | Electrical Photos
| FALSE | Kitchen | Starts Kitchen Build |  | AR Construction | Kitchen details in Purchase Agreement signed by Client. | Kitchen Finishes Purchase Agreement Signed
| FALSE | Kitchen | Purchase of Sink and Stove |  | Konti Design
PHASE 3 | FALSE | Interior Build | Finish Gypsum Board and Cement Board Installation |  | H&G Construction | Use link to see reference photos of this Category. | Interior Build Photos
| FALSE | Interior Build | Mudding and Sanding |  | H&G Construction
| FALSE | Interior Build | Priming Paint |  | H&G Construction
| FALSE | Interior Build | Flooring Installation |  | H&G Construction
| FALSE | Interior Build | Flooring Purchase |  | Konti Design | Flooring details in Purchase Agreement signed by Client. | Flooring Purchase Agreement Signed
| FALSE | HVAC | AC Units Purchase |  | Air Max | AC details in Purchase Agreement signed by Client. | AC Unit Purchase Agreement Signed
| FALSE | HVAC | AC Units Installation |  | D&G Air Conditioning | Use link to see reference photos of this Category. | HVAC Photos
| FALSE | Bathroom | Tiles, Saddle, Drain, and other (if applicable) Purchase |  | H&G Construction | Bathroom details in Purchase Agreement signed by Client. | Bathroom Finishes Purchase Agreement Signed
| FALSE | Bathroom | Tiles, Saddle, and other (if applicable) Installation |  | H&G Construction | Use link to see reference photos of this Category. | Bathroom Photos
| FALSE | Bathroom | Shower Head and Drain Installation |  | H&G Construction
| FALSE | Kitchen | Installation of cabinets and top... |  | AR Construction | Use link to see reference photos of this Category. | Kitchen Photos
| FALSE | Kitchen | Installation of sink and stove |  | AR Construction
PHASE 4 | FALSE | Plumbing Finishes | Plumbing finishes installed in Bathroom and Kitchen |  | H&G Construction | Use link to see reference photos of this Category. | Plumbing Photos
| FALSE | Electrical Finishes | Purchase of lightning fixtures, ceiling fans, and other electrical... |  | Konti Design | Purchased by Client | Interior Lighting Fixture Purchase Agreement
| FALSE | Electrical Finishes | Installation of lightning fixtures, ceiling fans, and other electrical... |  | H&G Construction | Use link to see reference photos of this Category. | Electrical Photos
| FALSE | Container Finishes | Interior Painting |  | H&G Construction | Enter details: color code, Egg Shell White | Container Finishes Photos
| FALSE | Container Finishes | Roof sealing and heat treatment |  | H&G Construction | Urethanizer 5 Gal. 100% Acrylic Urethane Elastomeric White Reflective Roof Sealer
| FALSE | Container Finishes | Exterior painting |  | H&G Construction | Enter details: color code - Dark charcoal blue and container doors and short side orange????
| TRUE | Container Installation | Transport Container to Site | DONE | MF Solution Corp | Use link to see reference photos of this Category. | Container Installation Photos
PHASE 5 | FALSE | Detailing | Purchase of vanity, toilet, sink faucet |  | Konti Design | Bathroom details in Purchase Agreement signed by Client. | Bathroom Furniture Purchase Agreement Signed
| FALSE | Detailing | Installation of vanity, toilet, sink faucet |  | H&G Construction | Use link to see reference photos of this Category. | Bathroom Photos
| FALSE | Detailing | Interior Door Purchase |  | Konti Design | Doors details in Purchase Agreement signed by Client. | Interior Doors Purchase Agreement Signed
| FALSE | Detailing | Installation of Interior Door |  | H&G Construction | Use link to see reference photos of this Category. | Interior Doors Photos
| FALSE | Detailing | Container Last Punchlist |  | H&G Construction | Use link to see reference photos of this Category. | Last Punchlist Photos
| FALSE | Post Construction Cleanup | Last clean up |  | Konti Design | Use link to see reference photos of this Category. | Cleanup Photos
EXTERIOR AND ADD-ONS | TRUE | Foundation | Depth and Location of footings (Survey Stakeout) | DONE | Jose Rivera | Use link to see reference photos of this Category. | Foundation Photos
| TRUE | Foundation | Rebar spacing | DONE | Ing. Jose Perez
| TRUE | Foundation | Screw protuding for container mounting | DONE | Ing. Jose Perez
| TRUE | Foundation | Pour concrete | DONE | Ing. Jose Perez
| TRUE | Foundation | Installation of containers welded to plates | DONE | Soldadura Rizoma
| FALSE | Outdoor Kitchen Build | Starts Kitchen Build |  | Konti Design | Outdoor Kitchen details in Purchase Agreement signed by Client. | Outdoor Kitchen Purchase Agreement Signed
| FALSE | Outdoor Kitchen Build | Kitchen Installation |  | AR Construction | Use link to see reference photos of this Category. | Outdoor Kitchen Photos
| FALSE | Appliances Purchase | Purchase of appliances |  | TBD | Appliances details in Purchase Agreement signed by Client. | Appliances Purchase Agreement Signed
| FALSE | Appliances Purchase | Installation of appliances |  | Manufacturer | Use link to see reference photos of this Category. | Appliances Photos
| FALSE | Solar Energy | Installation of Solar Energy |  | Transcon Lightning Systems | Use link to see reference photos of this Category. | Solar System Photos
| FALSE | Site Electric | Connect to Utilities |  | Ing. Jose Perez | Use link to see reference photos of this Category. | Site Electric Photos
| FALSE | Site Electric | Check-up to validate electrical connections |  | Ing. Jose Perez
| FALSE | Site Electric | Purchase of all exterior lightning and fixtures... |  | H&G Construction | Site Electric details in Purchase Agreement signed by Client.
| FALSE | Site Electric | Installation of all exterior lightning and fixtures... |  | H&G Construction | Use link to see reference photos of this Category.
| FALSE | Site Plumbing | Installation of all site plumbing (Sanitary, Septic System...) |  | H&G Construction | Use link to see reference photos of this Category. | Site Plumbing Photos
| FALSE | Site Plumbing | Verify operation and leaks |  | H&G Construction
| FALSE | Site Plumbing | Connect to Utilities |  | TBD
| FALSE | Septic System | Depth and Location of system |  | Andrea Camacho | Use link to see reference photos of this Category. | Septic System Photos
| FALSE | Septic System | Installation of System |  | Andrea Camacho
| FALSE | Pool | Enter Details if applies (Pool Size/ Type) |  | TBD |  | Pool Photos
| FALSE | Steel Structure | Installation of beams and columns |  | North Steel | Use link to see reference photos of this Category. | Steel Structure Photos
| FALSE | Steel Structure | Installation of containers welded to beams |  | North Steel
| FALSE | Steel Structure | Installation of stairwells |  | North Steel
| FALSE | Steel Structure | Installation of structural elements for decking (steel) |  | North Steel
| FALSE | Decking | Installation of structural elements for decking (wood) |  | H&G Construction | Use link to see reference photos of this Category. | Decking Photos
| FALSE | Decking | Installation of decking surface |  | H&G Construction
| FALSE | Decking | Installation of railing system |  | H&G Construction
| FALSE | Decking | Wood Sanding |  | H&G Construction
| FALSE | Decking | Exterior wood stain and sealer |  | H&G Construction
| FALSE | Decking | Installation of Pergola |  | H&G Construction
| FALSE | Decking | Installation of Pergola Roof |  | H&G Construction
| FALSE | Sitework | Landscaping |  | TBD | Use link to see reference photos of this Category. | Sitework Photos
| FALSE | Sitework | Driveway |  | Emilio Bierd
| FALSE | Project Hand-off | Final Hand-off Agreement |  | Konti Design
Note on B2: Insert Link

## Formula
TASK COMPLETION:
TOTAL | 39
DONE | 7
% | 17.95%
PHASES | TOTAL | DONE | %
PHASE 1 | 8 | 6 | 75%
PHASE 2 | 10 | 0 | 0%
PHASE 3 | 12 | 0 | 0%
PHASE 4 | 7 | 1 | 14.29%
PHASE 5 | 6 | 0 | 0%
TOTAL | 43 | 7 | 16.28%
EXTERIOR AND ADD-ONS | 34 | 5 | 14.71%