## Priorities (Prioridades)
# | Priority (Prioridad) | Status (Estado) | Page (Página) | Topic (Tema) | Cluster (Grupo) | Repetition n (Repetición) | Quote — verbatim (Cita textual) | Proposed fix (Solución propuesta) | Effort (Esfuerzo) | ETA bucket (Bucket ETA) | Linked task ref (Tarea ligada)
16 | P0 | ⏳ Pending (Pendiente) | https://konti-demo.replit.app/projects/proj-1 | Feature request (Solicitud) | Client view / portal | 12 | Agregar carga de archivos por parte del cliente o definir claramente si puede subir documentos y en qué sección | Add client-side document upload (or document where the client can upload), since today only the team uploads. | L | 1 week | —
17 | P0 | ⏳ Pending (Pendiente) | https://konti-demo.replit.app/projects/proj-1 | Feature request (Solicitud) | Client view / portal | 12 | Agregar pestaña de “Gastos no facturables” | Add a 'Gastos no facturables' (non-billable expenses) tab to the project finances panel. | M | 2–3 days | —
19 | P0 | ⏳ Pending (Pendiente) | https://konti-demo.replit.app/projects/proj-1 | Feature request (Solicitud) | Client view / portal | 12 | Agregar columnas de parte del cliente de monto total, pagado, saldo pendiente y estado por factura | Add per-invoice columns to the client invoices view (total, paid, balance, status). | M | 2–3 days | —
20 | P0 | ⏳ Pending (Pendiente) | https://konti-demo.replit.app/projects/proj-1 | Content (Contenido) | Client view / portal | 12 | En configuración del cliente agregar teléfono, dirección postal y dirección física | Make phone, postal address, and physical address editable in the client configuration screen. | S | ≤ 1 day | —
26 | P0 | ⏳ Pending (Pendiente) | https://konti-demo.replit.app/projects/proj-1 | Other (Otro) | Client view / portal | 12 | Que quede la ultima versión aquí, pero tengamos historial de los documentos. Pero solo se puede descargar la ultima versión | Keep only the latest version of each document downloadable, but expose a read-only version history alongside it. | M | 2–3 days | —
27 | P0 | ⏳ Pending (Pendiente) | https://konti-demo.replit.app/projects/proj-1 | Other (Otro) | Client view / portal | 12 | Ellos van a marcar que quieren que el cliente vea y que no | Add a per-document/per-section 'visible to client' toggle so the team controls exactly what the client sees. | L | 1 week | —
35 | P0 | ⏳ Pending (Pendiente) | https://konti-demo.replit.app/materials | Other (Otro) | Calculator / estimating | 12 | Para el contratista, subir los ultimos 3 recibos y que tome esto para actualizar el listado de caculadora de mano de obra | On the materials page, accept the contractor's last 3 receipts and update the labor-rate list automatically. | L | 1 week | Task #28
49 | P0 | ⏳ Pending (Pendiente) | https://konti-demo.replit.app/calculator?projectId=proj-1&tab=variance | Content (Contenido) | Calculator / estimating | 12 | esto deberia vivir en el dashboard para que Naino no tenga que encontrar esta pagina (que esta dificil de llegar a ella) para poder subir los recibos y categorizarlos. Project Name Categoria Subcategoria etc (ver excell de Jorge del project report) La idea de esta sección clasifique los recibos y las cantidades directamente dentro de este excell para que entonces el reporte pueda halar la informacion | Surface the receipts-upload entry point on the dashboard (today Naino has to dig through /calculator?tab=variance to upload + categorize them). | M | 2–3 days | —
52 | P0 | ⏳ Pending (Pendiente) | https://konti-demo.replit.app/materials | Content (Contenido) | Calculator / estimating | 12 | nosotros no trabajamos por hora. si miramos el reporte de Jorge, esta la labor por lump sums.. creo que aqui esta la confusion con estos tabs. | Switch the labor model from hourly to lump-sum so the calculator matches Jorge's report — restructure the labor tabs accordingly. | L | 1 week | —
53 | P0 | ⏳ Pending (Pendiente) | https://konti-demo.replit.app/calculator | Content (Contenido) | Calculator / estimating | 12 | intentamos importar el CSV de nuestro estimado inicial sheet de materiales. pero sale medio algarete... entiendo que el formato de las columnas no esta matching a nuestros estimados. Recuerda que el proposito de esta calculadora es que desde el principio podamos tener un estimado basado en los averages de nuestra data historica y que al el proyecto seguir prograsando nosotros podamos editarla. Usando los project reports Upload endpoit + translation? la idea es que esta calculadora se trabaje una vez y yo cambiando pies cuadrados pueda tener un buen estimado y luego que se convierta en poryecto podamos ir editando materiales y añadiendo materiales y labor especificos a ese proyecto. creo que esto lo debemos hablar mas en detalle | Build a CSV import endpoint that translates the team's estimating-sheet column names into the calculator's schema (so imports stop coming in 'medio algarete'). | M | 2–3 days | —
55 | P0 | ⏳ Pending (Pendiente) | https://konti-demo.replit.app/calculator | Content (Contenido) | Calculator / estimating | 12 | contractor calculator? la info de abajo suena mas como project information.. maybe esto es como la data del proyecto? cantidad de baños, pies cuadrados, contingencia, margen, cantidad de cocinas, cantidad de vagones, | Re-label the 'contractor calculator' fields as 'Project Information' (bathrooms, sq ft, contingency, margin, kitchens, etc.) so the model matches the team's mental model. | M | 2–3 days | —
56 | P0 | ⏳ Pending (Pendiente) | https://konti-demo.replit.app/calculator | Content (Contenido) | Calculator / estimating | 12 | esto se deberia ver como nuestro estimado con las secciones y resumenes y categorias organizadas. (ej - los costos de diseño, permisos, taxes and gov fees no estan saliendo) la informacion que sale dentro de los estimados debe salir aqui completa. | Show the calculator output with the team's full estimate sections (design costs, permits, taxes & gov fees, summaries) — today key sections are missing. | L | 1 week | —
57 | P0 | ⏳ Pending (Pendiente) | https://konti-demo.replit.app/calculator | Content (Contenido) | Calculator / estimating | 12 | deben salir todos los materiales automaticamente... esto es lo que nos confunde de la parte de imports? se supone que se reflejen aqui? | Auto-populate every imported material in the calculator (today the team thinks they have to pick one-by-one after import). | M | 2–3 days | —
58 | P0 | ⏳ Pending (Pendiente) | https://konti-demo.replit.app/calculator | Content (Contenido) | Calculator / estimating | 12 | que es effective? | Replace the ambiguous 'effective' column header with a self-explanatory label (or add a tooltip explaining what it means). | S | ≤ 1 day | —
59 | P0 | ⏳ Pending (Pendiente) | https://konti-demo.replit.app/calculator | Feature request (Solicitud) | Calculator / estimating | 12 | necesitamos poder editar base price, quantitiy, | Make base price and quantity editable inline in the calculator line-item table. | M | 2–3 days | —
66 | P0 | ⏳ Pending (Pendiente) | https://konti-demo.replit.app/projects/proj-1/report | Content (Contenido) | Calculator / estimating | 12 | este management fee de donde sale? lo podemos editar en el calculator? | Add an editable management-fee field in the calculator and feed it through to the client report. | M | 2–3 days | —
67 | P0 | ⏳ Pending (Pendiente) | https://konti-demo.replit.app/projects/proj-1/report | Content (Contenido) | Client view / portal | 12 | si esta pagina es para el cliente.. ellos deben ver las categorias no el BOM. | Restructure the client view of the report to show categories instead of the raw BOM. | M | 2–3 days | —
76 | P0 | ⏳ Pending (Pendiente) | https://konti-demo.replit.app/projects/proj-1776983841174 | Other (Otro) | Client view / portal | 12 | private to who? el team debe tener total visibilidad.. los clientes no | Default 'private' notes/documents to team-only and never expose them to the client (overlaps with #27). | S | ≤ 1 day | —
82 | P0 | ⏳ Pending (Pendiente) | https://konti-demo.replit.app/projects/proj-1776983841174 | Bug report (Reporte de bug) | Client view / portal | 12 | maybe es por ser el demo pero no me deja upload nada | Investigate why upload fails on the demo project ('no me deja upload nada') and fix the regression. | M | 2–3 days | Task #27, Task #30, Task #32
91 | P0 | ⏳ Pending (Pendiente) | https://konti-demo.replit.app/projects/proj-1/report | Content (Contenido) | Client view / portal | 12 | si acaso aqui es que debe estar el punchlist con los links a fotos como esta en el excell llamado "Client Punch list" Ahi tambien vive el "Contractor Monitoring" que da la data de si el contratista se atraso y porque.. a veces es justificado otras no y qjuiero que el cliente pueda ver eso para que entienda | Embed the 'Client Punch list' (with photo links) and the 'Contractor Monitoring' narrative on the report so the client sees both. | L | 1 week | —
92 | P0 | ⏳ Pending (Pendiente) | https://konti-demo.replit.app/projects/proj-1/report | Content (Contenido) | Client view / portal | 12 | si este es el client report, la data debe match el reporte que les enviamos con sus categorias correspondientes y toda la info que sale en el... | Re-key the client-report categories so they match the team's spreadsheet one-to-one (single source of truth). | L | 1 week | —
4 | P0 | ⏳ Pending (Pendiente) | https://konti-demo.replit.app/projects/proj-1 | Feature request (Solicitud) | Site photos / gallery | 6 | No encuentro la sección de fotos y notas de fotos o videos | Add a Photos & Notes section inside the project page (upload, comment, link from the report). | L | 1 week | —
14 | P0 | ⏳ Pending (Pendiente) | https://konti-demo.replit.app/projects/proj-1 | Content (Contenido) | Site photos / gallery | 6 | Sumaria la parte de fotos y comentarios | Add a Photos & Comments block to the project detail view alongside the existing tabs. | L | 1 week | —
15 | P0 | ⏳ Pending (Pendiente) | https://konti-demo.replit.app/projects/proj-1 | Content (Contenido) | Site photos / gallery | 6 | El informe de seguimiento del contratista debería mostrar retrasos, clima, problemas, cambios, incumplimientos y retrabajos. Lo ampliaria un poco más con la info. | Expand the contractor-monitoring report to surface delays, weather, issues, changes, breaches, and rework. | L | 1 week | Task #7, Task #11, Task #25
23 | P0 | ⏳ Pending (Pendiente) | https://konti-demo.replit.app/projects/proj-1 | Other (Otro) | Site photos / gallery | 6 | Quiere que sea automadministrable y que puedan subir las imagenes | Make the photo/notes gallery self-administrable so the team can upload images directly without engineering help. | L | 1 week | —
69 | P0 | ⏳ Pending (Pendiente) | https://konti-demo.replit.app/calculator?projectId=proj-1&tab=variance | Content (Contenido) | Site photos / gallery | 6 | we need a place to import the site photos for the weekly report and punchlist. not sure where this is? these should also be able to be categorized so they can get saved in the drive as : process photos (internal), or punchlist photos (client view) then they need to get categorized by task type (plubming, electric, foundation, etc... ) see item categories in Punchlist excell | Add a site-photos importer for the weekly report and punchlist with categories (process photos = internal, punchlist photos = client-visible). | L | 1 week | —
79 | P0 | ⏳ Pending (Pendiente) | https://konti-demo.replit.app/projects/proj-1776983841174 | Content (Contenido) | Site photos / gallery | 6 | ver documento de punchlist.. deberiamos poder ver las mismas categorias items, y links a las fotos del dive para que el cliente pueda visualizar su proyecto sin tener que visitar el site | Align the punchlist categories/items with the team's 'Client Punch list' spreadsheet and surface Drive photo links so the client can browse without visiting the site. | L | 1 week | —
3 | P0 | ⏳ Pending (Pendiente) | https://konti-demo.replit.app/projects/proj-1/report | Design (Diseño) | PDF report export | 5 | Lo dejaria en fondo blanco para una mejor visual o con la posibilidad de light | Add a light-mode option for the project report (default the background to white) so it reads cleanly when shared. | M | 2–3 days | —
93 | P0 | ⏳ Pending (Pendiente) | https://konti-demo.replit.app/projects/proj-1/report | Content (Contenido) | PDF report export | 5 | este entonces trataria de que fuera como el phase pie chart que tenemos en el punchlist vs otra vez budget | Add a phase pie-chart vs. budget visualization to the project report (mirroring the punchlist phase chart). | M | 2–3 days | —
94 | P0 | ⏳ Pending (Pendiente) | https://konti-demo.replit.app/projects/proj-1/report | Content (Contenido) | PDF report export | 5 | estas fases no deberian tener numeros, esto ya que en el punchlist que vamos a incluir abajo salen las fases de construccion que si tienen numeros y se correlacionan a traves de todos los docuementos enviados. Por ende, estas fases que son las macro se pueden quedar con su nombre... | Drop the numeric prefix from the macro phases on the report so they no longer collide with the construction-phase numbering. | S | ≤ 1 day | —
95 | P0 | ⏳ Pending (Pendiente) | https://konti-demo.replit.app/projects/proj-1/report | Content (Contenido) | PDF report export | 5 | "weather status" | Rename the 'weather status' label on the report header to the agreed copy. | S | ≤ 1 day | —
98 | P0 | ⏳ Pending (Pendiente) | https://konti-demo.replit.app/projects/proj-1/report | Design (Diseño) | Branding / logo | 3 | no me encanta el negro..esta muy agresivo.. creo que debemos usar la paleta de colores que tenemos en los excell | Repaint the report from solid black to the KONTi brand palette (Excel reference) for a softer client-facing look. | S | ≤ 1 day | —
21 | P1 | 🟡 In progress / scheduled (En progreso / programado) | https://konti-demo.replit.app/projects/proj-1 | Feature request (Solicitud) | Calculator / estimating | 12 | Agregar Recibos de compras – solo del lado de KONTi y que puede el sistema cotejarlos con el informe | Persist KONTi-side receipts across server restarts and cross-check them against the report (continuation of #22). | L | 1 week | Task #22, Task #27
34 | P1 | 🟡 In progress / scheduled (En progreso / programado) | https://konti-demo.replit.app/calculator | Other (Otro) | Calculator / estimating | 12 | Nos pasan el reporte formato para subirlo y que quede con ese formato | Accept the team's report-template upload and render the calculator output in that exact format. | M | 2–3 days | Task #22, Task #29
48 | P1 | 🟡 In progress / scheduled (En progreso / programado) | https://konti-demo.replit.app/dashboard | Content (Contenido) | Client view / portal | 12 | entendemos que esta parte deberia ir dentro de los proyectos y lo primero que vemos en el dashboard debe ser solamente active projects y recent activity. lo que esta en el screenshot debe estar dentro de cada proyecto y especifica para cada proyecto, no juntando la data de cada proyecto. Es overwhelming ver el total de todos los proyectos. | Restructure the dashboard to show only Active Projects + Recent Activity, and move the aggregated stats into each project page (#18 covers the construction-status card portion). | L | 1 week | Task #18
8 | P1 | 🟡 In progress / scheduled (En progreso / programado) | https://konti-demo.replit.app/projects/proj-2/report | Design (Diseño) | PDF report export | 5 | Poder editar las fechas de reportes y que aparezcan los reportes generados a un costado para imprimirlos o descargarlos la cantidad de veces que quisiéramos. | Make report dates editable and list every previously generated report alongside the page for re-download/print (Task #29 underway). | L | 1 week | Task #4, Task #29
5 | P1 | ⏳ Pending (Pendiente) | https://konti-demo.replit.app/dashboard | Feature request (Solicitud) | Other / cross-cutting | 3 | Me gusta esta sección. Le sumaria la posibilidad de hacer click en las actividades e ir a ver detalles | Make the activity-feed entries clickable so they deep-link to the related project / activity detail. | M | 2–3 days | —
7 | P1 | ⏳ Pending (Pendiente) | https://konti-demo.replit.app/projects/proj-1 | Feature request (Solicitud) | Other / cross-cutting | 3 | Quedaria pendiente una sección de logs de acciones del cliente en la plataforma | Add a client-action audit log on the project page (who did what and when). | L | 1 week | —
12 | P1 | ⏳ Pending (Pendiente) | https://konti-demo.replit.app/projects/proj-1 | Content (Contenido) | Other / cross-cutting | 3 | Cambiar texto a Cronograma del proyecto | Rename the timeline label on the project page to 'Cronograma del proyecto'. | S | ≤ 1 day | —
18 | P1 | ⏳ Pending (Pendiente) | https://konti-demo.replit.app/projects/proj-1 | Design (Diseño) | Branding / logo | 3 | Este gris oscuro es demasiado oscuro me parece; usar gris KONTi de marca https://drive.google.com/drive/folders/12JZdXlT1zTE8tBLS9S51O1NJXR1G_YJ2 | Soften the dark-gray header on the project page to the KONTi brand gray (per the brand-asset folder). | S | ≤ 1 day | —
87 | P1 | ⏳ Pending (Pendiente) | https://konti-demo.replit.app/permits | Content (Contenido) | Permits / OGPe | 3 | this should say "Permit Documentation" | Rename the permits header to 'Permit Documentation'. | S | ≤ 1 day | —
88 | P1 | ⏳ Pending (Pendiente) | https://konti-demo.replit.app/permits | Content (Contenido) | Permits / OGPe | 3 | we have the permits docs separated in the excell sheet by type of permit : PCOC, USO, Consulta de Ubicacion, etc. Can we do this here? | Split the permits view by permit type (PCOC, USO, Consulta de Ubicación, etc.) to mirror the team's spreadsheet. | M | 2–3 days | —
89 | P1 | ⏳ Pending (Pendiente) | https://konti-demo.replit.app/permits | Content (Contenido) | Permits / OGPe | 3 | la primera pagina del excell de permiso tiene la data legal del proyecto y todos los ingenieros que trabajaron en el mismo. eso es sumamente importante que salga aqui para lo que podamos llenar | Surface the legal/engineer header (project legal data + engineers of record) at the top of the permits view so the team can fill it in. | M | 2–3 days | —
97 | P1 | ⏳ Pending (Pendiente) | https://konti-demo.replit.app/projects/proj-1/report | Design (Diseño) | Branding / logo | 3 | este logo esta muy pequeño. | Increase the report logo size and tighten the header layout so it doesn't look squashed. | S | ≤ 1 day | —
40 | P1 | 🟡 In progress / scheduled (En progreso / programado) | https://konti-demo.replit.app/ai | Other (Otro) | AI assistant | 1 | Armar notas de las preguntas realizadas por el cliente | Auto-summarize the client's chat questions and persist them as project notes (Task #23 shipped UI; #30 schedules persistence). | L | 1 week | Task #23, Task #30
43 | P1 | 🟡 In progress / scheduled (En progreso / programado) | https://konti-demo.replit.app/ai | Other (Otro) | Project creation / phases | 1 | Sumar el punchlist como checklist para pasar de etapas | Promote the punchlist as the formal phase-advance gate and persist it across restarts (Task #25 shipped gate; #32 schedules persistence). | L | 1 week | Task #25, Task #32
11 | P2 | ⏳ Pending (Pendiente) | https://konti-demo.replit.app/projects/proj-1 | Feature request (Solicitud) | Documents / files | 2 | No veo la sección de Organizar la categoría “Acuerdos” por “Contratos y Acuerdos de compra” | Group project documents into 'Contratos' and 'Acuerdos de compra' categories (today the list is flat). | M | 2–3 days | —
80 | P2 | ⏳ Pending (Pendiente) | https://konti-demo.replit.app/projects/proj-1776983841174 | Content (Contenido) | Documents / files | 2 | how do you categorize the document? permits, punchlist, drawings, etc? | Add a document categorization picker on upload (permits, punchlist, drawings, etc.). | M | 2–3 days | —
2 | P3 | ⏳ Pending (Pendiente) | https://konti-demo.replit.app/materials | Content (Contenido) | Materials library | 1 | Agregar botón de AÑADIR MATERIALES | Add an 'AÑADIR MATERIALES' (Add Materials) button at the top of the materials library page. | S | ≤ 1 day | —
61 | P3 | ⏳ Pending (Pendiente) | https://konti-demo.replit.app/team | Content (Contenido) | Team directory | 1 | deberiamos poder upload personas nuevas para que tengamos el directorio de los contratistas y podamos ir uploading la informacion de ellos... a menos que esto sea solamente users de la plataforma?? | Add an upload flow for new contractor records so the directory grows beyond platform users. | M | 2–3 days | —
74 | P3 | ⏳ Pending (Pendiente) | https://konti-demo.replit.app/leads | Content (Contenido) | Leads intake | 1 | que son estos scores? | Add an inline legend on the leads list explaining what each score means (e.g., temperature, BANT components). | S | ≤ 1 day | —

## Clusters (Repetición)
Cluster (Grupo) | # of items (Cantidad) | Member item #s (Ítems miembros) | Highest priority (Prioridad máxima) | Recommended track (Vía recomendada)
Calculator / estimating | 12 | 21, 34, 35, 49, 52, 53, 55, 56, 57, 58, 59, 66 | P0 | Treat the calculator as a master template (categories, units, labor, contractor side, report format) and ship in one focused sprint.
Client view / portal | 12 | 16, 17, 19, 20, 26, 27, 48, 67, 76, 82, 91, 92 | P0 | Carve out a dedicated 'Client Portal' epic — a single, opinionated client view with controlled visibility, uploads, and per-section toggles.
Site photos / gallery | 6 | 4, 14, 15, 23, 69, 79 | P0 | Build a self-administrable gallery (upload, captions, links from report) — single feature, single owner.
PDF report export | 5 | 3, 8, 93, 94, 95 | P0 | Ship the saved-report-template work (Task #29) and add re-download history on the report page.
Branding / logo | 3 | 18, 97, 98 | P0 | Single design pass: logo size, brand grays, light mode, palette consistency across report + project pages.
Other / cross-cutting | 3 | 5, 7, 12 | P1 | Triage individually — each item is a small, isolated change.
Permits / OGPe | 3 | 87, 88, 89 | P1 | Refresh the permits page (legal header, per-type split, design subsection) in a single visual pass.
Documents / files | 2 | 11, 80 | P2 | Add categories (Contratos / Acuerdos), client-side upload, and version history; defer Drive integration.
AI assistant | 1 | 40 | P1 | Polish the assistant's output rendering and persist client-question notes (already in motion via #23/#30).
Leads intake | 1 | 74 | P3 | Tighten the leads list copy to read as a pipeline.
Materials library | 1 | 2 | P3 | Add 'Add Material' affordance + price history per material.
Project creation / phases | 1 | 43 | P1 | Group the project-page enhancements (phase parallelism, sub-phases, naming, photos) into one project-detail polish pass.
Team directory | 1 | 61 | P3 | Quick copy fix (rename to Nainoshka) — bundle with any next team-page change.

## Roadmap (Hoja de Ruta)
ETA bucket (Bucket ETA) | # of items (Cantidad) | Estimated days (Días estimados) | Cumulative days (Días acumulados) | Item #s in bucket (Ítems en bucket) | Highest priority (Prioridad máxima)
≤ 1 day | 12 | 12 | 12 | 2, 12, 18, 20, 58, 74, 76, 87, 94, 95, 97, 98 | P0
2–3 days | 20 | 60 | 72 | 3, 5, 11, 17, 19, 26, 34, 49, 53, 55, 57, 59, 61, 66, 67, 80, 82, 88, 89, 93 | P0
1 week | 19 | 95 | 167 | 4, 7, 8, 14, 15, 16, 21, 23, 27, 35, 40, 43, 48, 52, 56, 69, 79, 91, 92 | P0

## OOS deferred (Fuera de alcance)
# | Page (Página) | Topic (Tema) | Quote — verbatim (Cita textual) | Why deferred (Por qué se difiere) | Linked task ref (Tarea ligada)
13 | https://konti-demo.replit.app/projects/proj-1 | Content (Contenido) | A veces las fases van en paralelo. ¿Qué pasa entonces? Podemos armar otra visual o se puede hacer en paralelo? | Parallel-phase visualization — needs design walkthrough; current model assumes serial phases. | —
22 | https://konti-demo.replit.app/projects/proj-1 | Content (Contenido) | Quieren actualizarlo 1 vez a la semana | 'Update once a week' — process expectation, not a product change. | —
24 | https://konti-demo.replit.app/projects/proj-1 | Other (Otro) | Conectado a ASana. Si se marca lista en asana o aquí se traslada | Asana sync request — defer until the integration plan is approved. | —
25 | https://konti-demo.replit.app/projects/proj-1 | Feature request (Solicitud) | El respositorio de los datos tiene que estar en el Drive. Puede haber un tilde de subir al Drive o a una base de dato | Drive as the canonical document store — third-party integration (Drive API, auth, mirroring rules) needs scoping. | —
47 | https://konti-demo.replit.app/dashboard | Other (Otro) | Grabar video demo, para compartir antes para que vayan a la reunion con las preguntas listas | Demo-video recording — operations request, not a product change. | —
50 | https://konti-demo.replit.app/calculator?projectId=proj-1&tab=variance | Content (Contenido) | cual es la funcionalidad de esta seccion? no entiendo lo que va a alimentar? | Variance-tab purpose unclear — needs walkthrough to confirm intent. | —
51 | https://konti-demo.replit.app/calculator?projectId=proj-1&tab=variance | Content (Contenido) | no entedemos este tab tampoco.. | Variance-tab purpose unclear — needs walkthrough to confirm intent. | —
54 | https://konti-demo.replit.app/calculator | Content (Contenido) | esto es para que nosotros ahora lo hagamos y ustedes puedan trabajar el template? no entendemos como funciona esto | Workflow ('we fill the template, you build it?') needs a walkthrough before scoping. | —
60 | https://konti-demo.replit.app/calculator | Content (Contenido) | lo que necesitamos es que tengamos una sola calculadora con toda la data que sale en el excell de jorge y que cada proyecto cree una copia editable... no estamos seguros como eso ocurre aqui en estos momentos. | Single shared calculator with per-project copies — large data-model change; needs design walkthrough. | —
62 | https://konti-demo.replit.app/projects/proj-1 | Other (Otro) | esto esta conectado a asana? | Asana sync question for the project page — defer until integration plan is approved. | —
63 | https://konti-demo.replit.app/projects/proj-1 | Other (Otro) | que significa esto? | Copy clarification ('what does this mean?') — needs walkthrough to identify which element. | —
64 | https://konti-demo.replit.app/projects/proj-1/report | Content (Contenido) | esto es client view o konti view? | Client-view vs. KONTi-view question on the report — already supports both; needs walkthrough to confirm closed. | —
65 | https://konti-demo.replit.app/projects/proj-1/report | Content (Contenido) | de donde se estan alimentando estas catergorias? | Source-of-categories question on the report — needs walkthrough to confirm closed. | —
68 | https://konti-demo.replit.app/projects/proj-1/report | Content (Contenido) | sera que esta pagina es el "punchlist"? | 'Is this page the punchlist?' — needs walkthrough to confirm intent. | —
70 | https://konti-demo.replit.app/ai | Feature request (Solicitud) | is this bot only to ask questions on KONTi side? i thought it was supposed to help Nai write the weekly reports on site? | Scope of the AI assistant (KONTi-only vs. client-facing) — product decision needed. | —
71 | https://konti-demo.replit.app/ai | Content (Contenido) | where does this information get updated or requested to the client? | Where info-requests get sent to the client — workflow decision needed. | —
72 | https://konti-demo.replit.app/ai | Other (Otro) | is this supposed to be how we communitcate change orders, material specs and such? | AI assistant for change orders / material specs — workflow decision needed. | —
73 | https://konti-demo.replit.app/leads | Content (Contenido) | no entiendo esta pagina? se supone que sea un crm? o esta conectado a asana y eso son los proyectos que van entrando a propuesta? | Leads page purpose (CRM vs. Asana mirror) — product decision needed. | —
75 | https://konti-demo.replit.app/leads | Content (Contenido) | ok me parece que esta conectado a asana y veo que de aqui los puedo crear a un proyecto nuevo cuando aceptan propuesta... la pregunta es en asana se crea el proyecto en base al template? no entiendo como funcioana | Asana mirror confirmed — defer until Asana integration scope is approved. | —
77 | https://konti-demo.replit.app/projects/proj-1776983841174 | Content (Contenido) | no entiendo que hace esto? que es lo que calcula en base a zoning y tipo de proyecto? | Zoning-based calculator unclear — needs walkthrough to confirm intent. | —
78 | https://konti-demo.replit.app/projects/proj-1776983841174 | Content (Contenido) | se supone que esto es para añadir mas items especiales al punchlist que va a estar completo aqui segun el documento? | Punchlist 'special items' question — needs walkthrough to confirm intent. | —
81 | https://konti-demo.replit.app/projects/proj-1776983841174 | Content (Contenido) | if this is how i send the clients docuements they need to sign, does this generate an email like we spoke automatically so that they get the notification explaining what the docuemnt is and what we need from them? | Auto-email on signature request — depends on the notifications integration plan; defer. | —
83 | https://konti-demo.replit.app/calculator?projectId=proj-1776983841174&tab=variance | Content (Contenido) | nos parece que esto significa que cada vez que queremos hacer un estimado hay que seleccionar cada material individualmente??? si es asi definitivamente no nos ayuda. La carta de materiales a cada proyecto debe ser estandar y editable pero no partir de cero. maybe no entendemos como es que va a funcionar.. | 'Pick each material individually?' — overlaps with #57 import auto-populate; revisit after that lands. | —
84 | https://konti-demo.replit.app/permits | Other (Otro) | esto esta leyendo el drive? | Drive-permits read — depends on the Drive integration; defer. | —
85 | https://konti-demo.replit.app/permits | Content (Contenido) | are these required signatures form the client only? how do we upload the documents? or is this reading the excell sheet in the drive? | Signature source / Drive read for permits — depends on Drive + signatures integration; defer. | —
86 | https://konti-demo.replit.app/permits | Content (Contenido) | once approved and final document is uploaded either to a folder in the drive where this system can match it? how does the client download the final document? | Final-document hand-off and download flow for permits — needs walkthrough. | —
90 | https://konti-demo.replit.app/projects/proj-1/report | Content (Contenido) | no entiendo esta parte.. es como las instrucciones par el cliente que sepa lo que le toca? | Client-instructions section on the report — needs walkthrough to confirm intent. | —
96 | https://konti-demo.replit.app/projects/proj-1/report | Other (Otro) | esto simplemente esta leyendo asana ?? | Asana-read question for the report — defer until the integration plan is approved. | —

## Methodology (Metodología)
Section (Sección) | Detail (Detalle)
Source (Fuente) | Built from the 98-item KONTi feedback inbox and the existing report at attached_assets/reports/feedback-vs-changelog.md. Status, page, refs, and quote are reused verbatim from the inbox and report — this workbook does not re-classify them.
Scope (Alcance) | The Priorities sheet covers every actionable item (45 Pending + 6 In progress = 51 rows). The 19 Completed items are intentionally not re-listed; see the existing report's Completed appendix. The 28 Out-of-scope items are kept on their own sheet so nothing is lost.
Priority rubric (Rúbrica de prioridad) | P0 — Critical: confirmed bug reports, broken core flows, or items in a cluster of size ≥ 5. P1 — High: items already In progress, single items on a high-traffic page (Project Detail, Calculator, AI, Dashboard, Report), or cluster size 3–4. P2 — Medium: cluster size 2. P3 — Low: cluster size 1 outside critical paths.
Repetition counting (Conteo de repetición) | Two-pass: a keyword/page heuristic groups items into clusters (Client view / portal, Calculator, Site photos, etc.); a manual review pass re-buckets the obvious mis-classifications. The cluster size is the count of *actionable* items (Pending + In progress) in the cluster — Out-of-scope items are not counted toward cluster repetition.
ETA buckets (Buckets ETA) | ≤ 1 day (1d): copy / labels / small CSS. 2–3 days (3d): single-component refactor or small UI feature. 1 week (5d): page-level feature or small backend route. 2 weeks (10d): feature spanning multiple pages or new persistence. 3+ weeks (15d+): new module (Client Portal, Calculator master template).
Roadmap totals (Totales de hoja de ruta) | The Roadmap sheet multiplies the bucket count by its representative day-cost (1, 3, 5, 10, 15) so the team has a back-of-envelope estimate per bucket and a cumulative-days column to scope a sprint.
Quotes (Citas) | All quotes are preserved verbatim — Spanish stays Spanish, English stays English. Item numbers match the existing report's per-item cards (Item 1 = oldest by creation time; Item 98 = newest).
Out of scope (Fuera de alcance) | Doing the actual fixes — this workbook is the prioritized plan only. Editing inbox state. Replacing the existing feedback-vs-changelog report. Re-generating the PDF report (already delivered).
How to use (Cómo usar) | (1) Filter the Priorities sheet by Priority + ETA bucket to scope the next sprint. (2) Open the Clusters sheet to spot the largest themes. (3) Use the Roadmap sheet to commit a sprint by cumulative days. (4) Keep the Out-of-scope sheet visible so deferred items get walked through later.